## To share
TIMELINE ANTICIPATED FOR 2013 ANNUAL & WI REPORTS | BY | DONE | VIA | NOTES | NOTES for 2014 Reports | Email, File, Memo, Phone
JUNE of 2013
Request BP write-up from DJS | YE
Request Symposium write-up from MH | YE
Basic template updates, i.e. change year | YE
JULY of 2013
Determine BP pictures to use & inform YE | TF
Determine Symposium pictures to use & inform YE | TF
Bradley Prizes write-up completed; to YE | DJS
Symposium write-up completed; to YE | MH
BP write-up done in AR-draft | YE
Symp write-up done in AR-draft | YE
Place BP pictures | YE
Place Symposium pictures | YE
AUGUST of 2013
Contact Lithoprint to request quote | YE
Ask MWG if any major style changes to AR | YE
Ask MWG if any major style changes to R-WI | YE
Confirm GCCs, BPS, BF handled same as prior year | YE
MWG response received re AR changes | YE
MWG response received re R-WI changes | YE
Convey MWG request for style changes, if any, to program staff | YE
Take count of reports left from two years ago, for TF | YE
SEPTEMBER of 2013
Directors photo provided to YE | TF
Lithoprint quote received | YE
Prepare AR & R- WI budgets; to TF | YE
Request cover samples from printer | YE
Receive cover samples | YE
OCTOBER of 2013
Determine quantity of AR | TF/YE
Determine quantity of R-WI | TF/YE
Determine quantity of President enclosure cards | TF
Determine cover stock & color | TF
Determine Inside stock & color | TF
Receive style changes from Program staff for AR, if any | YE
Receive style changes from Program staff for R-WI, if any | YE
NOVEMBER of 2013
Ask TF to request updated mail lists (GMC, DF, MMAC) | YE
Request sector descrip text changes from program staff | YE
Provide staff photo to YE | TF
Staff photo received and placed into AR | YE
Staff photo received and placed into R-WI | YE
Ask MWG: cover letter w/WI Rept (encl. Sample) | YE
AR text and style changes completed | YE
R-WI text and style changes completed | YE
Grants list to program staff for editing of descriptions | YE
OR Use descriptions already on website from MH | YE
Sector description text changes to YE | PS
Sector description text changes completed | YE
DECEMBER of 2013
Provide web-site list of grants to YE | MH
Updated mail lists to YE | TF
Update GMC, DF, MMAC mail lists in E-Tapestry | YE
Run report & export grants from Gifts | YE
Format exported lists for AR | YE
Format exported lists for R-WI | YE
Run Gifts mailing list | YE
Run E-Tapestry mailing list | YE
Combine Gifts and e-Tapestry mail lists | YE
Provice AR mail list for DK to route to program staff | YE
Enter grants into AR document | YE
Enter grants into R-WI document | YE
Run grant tape totals; check all grants entered on AR | YE
Run grant tape totals; check all grants entered on R-WI | YE
Provide AR draft to Program Staff | YE
Provide R-WI draft to Program Staff | YE
Staff changes on AR returned to YE | PS
Staff changes on R-WI returned to YE | PS
Program Staff changes made to AR | YE
Program Staff changes made to R-WI | YE
Provide AR draft to MH | YE
AR draft returned to YE | MH
MH changes to AR completed | YE
Run grant tape total; check all grants entered on AR | YE
Run grant tape total; check all grants entered on R-WI | YE
Prepare reconciliation of grants to financial statement | YE
Provide AR draft to CF w/reconciliation to financial stmt | YE
AR draft returned to YE | CF
Changes to AR completed | YE
Provide AR draft to MWG | YE
AR draft returned to YE | MWG
MWG changes to AR completed | YE
Provide R-WI draft to MH | YE
R-WI draft returned to YE | YE
MEH changes to R-WI completed | YE
Provide R-WI draft to CF w/tape totals attached | YE
R-WI draft returned to YE | CF
Changes to R-WI completed | YE
Provide R-WI draft to MWG | YE
R-WI draft returned to YE | MWG
MWG changes to R-WI completed | YE
JANUARY of 2014
Select foil and ink colors | TF
Return mail list changes to YE | DK
Recommended mail list changes to MWG | YE
Mail list changes returned to YE | MWG
AR mail list changes completed | YE
R-WI mail list prepared (pulled from AR mail list) | YE
R-WI mail list to MWG for review | YE
R-WI mail list returned to YE | MWG
R-WI mail list completed | YE
Send AR mail list to printer | YE
Send R-WI mail list to printer | YE
President's letter for R-WI to YE (if needed) | MWG
Draft of President's letter completed | YE
Final of President's letter completed | YE
Letters printed in-house for printer to enclose | YE
Provide final AR draft to MWG/CF/DPS/TF for sign off (ex: FiHi) | YE
Provide final R-WI draft to MWG/CF/DPS/TF for sign off | YE
AR draft returned to YE | VPs
R-WI draft returned to YE | VPs
Changes to AR completed | YE
Changes to R-WI completed | YE
FEBRUARY of 2014
AR mail list sent to printer | YE
R-WI mail list sent to printer | YE
Financial Highlights to YE (as soon after Feb. brd mtg as possible) | MLH
Financial highlights page prepared | YE
Draft of financial highlights to MLH for review | YE
Changes to financial highlights to YE | YE
Changes to financial highlights completed | YE
Draft of financial highlights to CF for review & sign off | YE
Any changes to financial highlights to YE | CF
Changes to financial highlights completed | YE
Draft of financial highlights to MWG for approval | YE
Financial highlights returned to YE | MWG
Financial highlights completed in AR | YE
MARCH OF 2014
AR packaged by software | YE
R-WI packaged by software | YE
AR CD prepared for printer | YE
R-WI CD prepared for printer | YE
Print color copy of AR for printer | YE
Print color copy of R-WI for printer | YE
CD of AR sent to printer w/color copy print-out | YE
CD of R-WI sent to printer w/color copy print-out | YE
President's letter sent to printer | YE
AR proof received | YE
AR proof reviewed | YE
AR proof reviewed, signed off | CF
AR proof reviewed, signed off | DPS
R-WI proof received | YE
R-WI proof reviewed | YE
R-WI proof reviewed, signed off | CF
R-WI proof reviewed, signed off | DPS
Changes to AR returned to printer (if any) | YE
Changes to R-WI returned to printer (if any) | YE
New proofs received & reviewed | YE
AR proof acceptance form signed and returned to printer | CF
R-WI proof acceptance form signed and returned to printer | CF
20 AR received | LP
20 R-WI received | YE
AR mailed by printer | YE
R-WI mailed by printer | LP
Remainder AR delivered to Fdn. | YE
Remainder R-WI delivered to Fdn. | LP
Copy to each staff member | YE
Email staff re: new AR left on their desk (check w/MWG 1st) | YE
Invoice received | YE
AR budget document updated | YE
PDF versions emailed to MH | YE

## SignForm
REPORT | VERSION | DATED | ON | TO | REVIEWED; RETURNED ON | CHANGES NEEDED? | CHANGES DONE ON

## Track Form
ANNUAL REPORT
REVIEWER | VERSION # | ON | CHANGES NEEDED | CHANGES MADE | CHANGES APPROVED IN VERSION # | CHANGES APPROVED IN VERSION # | CHANGES APPROVED IN VERSION #
Mike H. | A1 | 2013-02-25 | YES | YES | A2: no | A3:
Dan
Alicia
Jan
Cynthia
Grebe
WI REPORT
REVIEWER | VERSION # | ON | CHANGES NEEDED | CHANGES MADE | CHANGES APPROVED IN VERSION # | CHANGES APPROVED IN VERSION # | CHANGES APPROVED IN VERSION #
Mike H. | A1 | 2013-02-25 | YES | YES
Dan
Alicia
Jan
Cynthia
Grebe
OR
ANNUAL REPORT
VERSION # | A1
DATED | 2013-02-25
TO: | MEH
ON: | 2013-02-26
CHANGES NEEDED? | YES
CHANGES MADE | YES
CHANGES REVIEWED | YES
CHANGES NEEDED? | YES
CHANGES MADE | YES
CHANGES REVIEWED | YES
CHANGES NEEDED? | NO
CHANGES MADE
SIGNED-OFF BY:
DATE
WISCONSIN REPORT
VERSION #
DATED
TO:
ON:
CHANGES NEEDED?
CHANGES MADE