## Orig 2011 T.L. by month
ORIGINAL TIMELINE MONTH ANTICIPATED | BY | 2012 Rept | NOTES | 2013 Rept | NOTES
JUNE of 2012
Request BP write-up from DJS | YE
Request Symposium write-up from MH | YE
JULY of 2012
Determine BP pictures to use | MWG/TF
Determine Symposium pictures to use | MWG/TF
Bradley Prizes write-up completed; to YE | DJS
Symposium write-up completed; to YE | MEH
BP write-up done in AR-draft | YE
Place BP pictures | YE
Symp write-up done in AR-draft | YE
Place Symposium pictures | YE
AUGUST of 2012
Draft AR and R-WI budgets | YE
Contact Lithoprint to request quote | YE
Contact EXG to request quote | YE
Ask MWG if any major style changes to AR | YE
Ask MWG if any major style changes to WI-R | YE
MWG response received re AR changes | YE
MWG response received re WI-R changes | YE
Convey MWG request for changes to program staff | YE
Confirm GCCs, BPS, BF handled same as prior year | YE
Take count of reports left from two years ago | YE
SEPTEMBER of 2012
Directors photo provided to YE | TF
Lithoprint quote received | YE
EXG quote received | YE
Prepare final budget | YE
Request cover samples from printer | YE
Receive cover samples | YE
OCTOBER of 2012
Determine quantity of AR | TF/YE
Determine quantity of WI Report | TF/YE
Determine quantity of President enclosure cards | TF
Determine cover stock & color | TF/YE
Determine Inside stock & color | TF/YE
Receive style changesfrom MWG for AR, if any | YE
Receive style changes from MWG for R-WI, if any | YE
NOVEMBER of 2012
Request program area text description changes, if any | YE
Request updated mailing lists (GMC, DF, MMAC) | TF
Provide staff photo to YE | TF
Staff photo received and placed into AR | YE
Staff photo received and placed into WI-R | YE
Ask MWG-cover letter w/WI Rept (enc. Sample) | YE
AR text and style changes (if any) to YE | YE
AR text and style changes (if any) to YE | YE
Grants list to program staff for editing of descriptions | YE
DECEMBER of 2012
Update GMC, DF, MMAC mail lists in E-Tapestry | YE
Text and style changes completed for AR | YE
Text and style changes completed for R-WI | YE
Export grants from Gifts | YE
Format exported lists for AR | YE
Format exported lists for R-WI | YE
Provide web-site list of grants to YE | MEH
Enter grants into AR document | YE
Provide AR draft to Program Staff | YE
Staff changes on AR returned to YE | VP
Program Staff changes made | YE
Provide AR draft to MWG/MEH | YE
Select foil and ink colors | TF/YE
Draft returned to YE | MWG
MWG changes to AR completed | YE
Run grant tape total; check all grants entered on AR | YE
Run Gifts mailing list | YE
Run E-Tapestry mailing list | YE
Combine Gifts and e-Tapestry mail lists | YE
Prepare and circulate AR mail list to staff | YE
Return mail list changes to YE | PS
AR mail list changes completed | YE
JANUARY of 2013
Enter grants into R-WI document | YE
Send AR mail list to printer | YE
President's letter for R-WI to YE | MWG
Draft of President's letter completed | YE
Final of President's letter completed | YE
Provide R-WI draft to Program Staff | YE
Changes to R-WI returned to YE | Staff
Changes made to R-WI | YE
Provide R-WI draft to MWG/CF/TF/MH | VP
Changes to R-WI returned to YE | VP
Changes to R-WI completed | YE
Run grant tape total; check all grants entered on R-WI | YE
Continue with changes and review by staff of AR | YE
Continue with changes and review by staff of R-WI | YE
Prepare and circulate R-WI mail list | YE
Return R-WI mail list changes to YE | Staff
FEBRUARY of 2013
R-WI mail list changes completed | YE
R-WI mail list sent to printer | YE
Financial Highlights to YE (after board meeting) | MLH
Draft of financial highlights to MLH for review | YE
Prepare reconciliation of grants to financial statement | YE
Provide final AR w/reports, tape totals & recon. to CF | YE
Final review of AR returned to YE | CF
Final AR changes made | YE
AR packaged by software | YE
AR CD prepared for printer | YE
AR CD sent to printer w/color copy | YE
Provide final R-WI w/reports, tape totals to CF | YE
Final review of R-WI returned to YE | CF
Final R-WI changes made | YE
R-WI packaged by software | YE
R-WI CD prepared for printer | YE
R-WI CD sent to printer w/color copy | YE
Print president's letter on letterhead | YE
President's letter sent to printer | YE
AR proof received | YE
AR proof reviewed | YE
AR proof acceptance form signed and returned | YE
R-WI proof received | YE
R-WI proof reviewed | YE
R-WI proof acceptance form signed and returned | YE
20 AR received | YE
20 R-WI received | YE
AR mailed by printer | LP
R-WI mailed by printer | LP
Remainder AR delivered to Fdn. | LP
Remainder R-WI delivered to Fdn. | LP
Copy to each staff member | YE
Email to staff re: copy of the reports left on their desk | YE
Invoice received | YE

## Sorting
MONTH ANTICIPATED | MONTH | BY | DATE DONE FOR 2012 REPORT | ANSWER OR RETURN REQUIRED? DATE REC'D. | NOTES / PROGRESS
Prepare 2012 AR timeline | 6 | YE | 2012-03-28
To Terri for approval | 6 | TF
Draft timeline email to TF for approval | 6 | YE
Any changes made | 6 | TF
Email AR timeline with note to staff | 6 | YE
Ask MWG if there will be any style changes to AR | 7 | YE
Ask MWG if there will be any style changes to R-WI | 7 | YE
Provide MWG with sample Pres. Let for R-WI w/req if want to use or change | 7 | YE
Ask MWG if GCCs, BPS, BF, Donor Int. handled same as prior year | 7 | YE
Request BP write-up from DJS | 7 | YE
Request Symposium write-up from MH | 7 | YE
Bradley Prizes write-up completed and to YE | 7 | DJS
Symposium write-up completed and to YE | 7 | MEH
Determine BP pictures to use | 8 | YE/TF
Determine Symposium pictures to use | 8 | YE/TF
BP write-up done in AR-draft | 8 | YE
Symp write-up done in AR-draft | 8 | YE
Place BP pictures | 8 | YE
Place Symposium pictures | 8 | YE
Provide YE with style changes for AR | 9 | MWG
Provide YE with style changes for R-WI | 9 | MWG
Contact Lithoprint to request quote | 9 | YE
Contact EXG to request quote | 9 | YE
Take count of reports left from two years ago | 9 | YE
Discuss quantity with Terri | 9 | YE
Determine quantity of President enclosure cards | 9 | YT/TF
Lithoprint quote received by | 9 | YE
EXG quote received by | 9 | YE
Draft AR and R-WI budgets | 9 | YE
Prepare final budget | 9 | YE
Submit budget to TF | 9 | YE
Draft of President's letter completed, if used | 9 | YE
Final of President's letter completed, if used | 9 | YE
Style changes to AR completed | 10 | YE
Style changes to AR approved | 10 | YE
Style changes to R-WI completed | 10 | YE
Style changes to R-WI approved | 10 | YE
Staff photo provided to YE | 10 | YE
Staff photo placed in report | 10 | YE
Directors photo provided to YE | 10 | YE
Director photo placed in reports | 10 | YE
Request cover samples from printer | 10 | YE
Receive cover samples | 10 | YE
Review and narrow down cover choices | 10 | YE
Determine cover stock and color | 10 | YE/TF
Inform printer of quantity, color, cover stock | 10 | YE
Select foil and ink colors | 10 | YE/TF
Inform printer of foil and ink choices | 10 | YE
Request updated program area text descriptions, if needed | 10 | YE
Ask TF to request updated mail lists from: DF, MMAC, GMC | 10 | YE
Update DF mail list in e-Tapestry | 11 | YE
Updte MMAC mail list in e-Tapestry | 11 | YE
Update GMC mail list in e-Tapestry | 11 | YE
Run e-Tapestry mail list | 11 | YE
Run Gifts mail list | 11 | YE
Combine Gifts and e-Tapestry lists | 11 | YE
Format mail list | 11 | YE
Circulate AR mail list to staff w/memo to review | 11 | YE
Return AR mail list changes to YE | 12 | PS
Give recommended changes to MWG for review and approval | 12 | YE
Ask Mike H. for grants listing on web site | 12 | YE
Run Gifts report of AR grants | 12 | YE
Run Gifts report of R-WI grants | 12 | YE
Grants listing from web site to YE | 12 | MEH
Update Keiser grant page in AR | 12 | YE
Inform YE ok make recommended updates to mail list | 1 | MWG
Update mail list | 1 | YE
Enter AR grants into document according to categories provided by Mike/Dan | 1 | YE
Enter R-WI grants into document alphabetically | 1 | YE
R-WI Page 6 (let to cmty) to MWG for approval of updates | 1 | YE
Print and review 1st draft of AR | 1 | YE
Print and review 1st draft of R-WI | 1 | YE
Run grant tape total; check all grants entered on R-WI | 1 | YE
Run grant tape totals; check all grants entered on AR | 1 | YE
Verify icons in R-WI | 1 | YE
Route AR draft to Program Staff | 1 | YE
Route R-WI draft to Program Staff | 1 | YE
Return AR changes to YE | 1 | PS
Return R-WI changes to YE | 1 | PS
Staff changes to AR completed | 1 | YE
Staff changes to R-WI completed | 1 | YE
Confirm with printer how mailing will be handled | 1 | YE
To MH for final review of AR | 2 | YE
Return final AR draft to YE | 2 | MH
Final AR changes made | 2 | YE
To MH for final review of R-WI | 2 | YE
Return final R-WI draft to YE | 2 | MH
Final R-WI changes made | 2 | YE
Ask Stephanie to proof AR | 2 | YE
Ask Stephanie to proof R-WI | 2 | YE
AR proofed | 2 | SR
R-WI proofed | 2 | SR
SR's changes made to AR | 2 | YE
SR's changes made to R-WI | 2 | YE
Prepare AR reconciliation with Gifts & financial statements for CF | 2 | YE
Prepare R-WI reconciliation with Gifts for CF | 2 | YE
Provide AR final draft to MWG/CF/TF | 2 | YR
Return AR changes to YE | 2 | CF
Return AR changes to YE | 2 | MWG
Changes to AR completed | 2 | YE
Financial Highlights to YE | 2 | MLH
Financial highlights entered | 2 | YE
Draft of financial highlights to MLH for review | 2 | YE
Changes to financial highlights returned to YE | 2 | MLH
Final changes made to financial highlights | 2 | YE
Financial highlights approved | 2 | MLH
InDesign "package" procedure completed for AR | 3 | YE
InDesign "package" procedure completed for R-WI | 3 | YE
AR CD prepared for printer | 3 | YE
AR CD sent to printer w/color copy | 3 | YE
R-WI CD prepared for printer | 3 | YE
R-WI CD sent to printer w/color copy | 3 | YE
President's letter sent to printer | 3 | YE
AR proof received | 3 | YE
AR proof reviewed | 3 | YE
AR changes made by printer and returned for approval | 3 | YE
AR proof acceptance form signed and returned | 3 | YE
R-WI proof received | 3 | YE
R-WI proof reviewed | 3 | YE
R-WI changes made by printer and returned for approval | 3 | YE
R-WI proof acceptance form signed and returned | 3 | YE
20 AR received | 4 | YE
20 R-WI received | 4 | YE
AR mailed | 4 | LP
R-WI mailed | 4 | LP
Remainder AR delivered | 4 | LP
Remainder R-WI delivered | 4 | LP
Copy to each staff member | 4 | YE
Email to staff re: copy of the reports left on their desk | 4 | YE
Invoice received | 5 | YE
Invoice submitted | 5 | YE

## To share
TIMELINE ANTICIPATED FOR 2013 ANNUAL & WI REPORTS | BY | DONE | NOTES | NOTES for 2014 Reports
JUNE of 2013
Request BP write-up from DJS | YE
Request Symposium write-up from MH | YE
JULY of 2013
Determine BP pictures to use & inform YE | MWG/TF
Determine Symposium pictures to use & inform YE | MWG/TF
Bradley Prizes write-up completed; to YE | DJS
Symposium write-up completed; to YE | MEH
BP write-up done in AR-draft | YE
Place BP pictures | YE
Symp write-up done in AR-draft | YE
Place Symposium pictures | YE
AUGUST of 2013
Contact Lithoprint to request quote | YE
Contact EXG to request quote | YE
Ask MWG if any major style changes to AR | YE
Ask MWG if any major style changes to R-WI | YE
Confirm GCCs, BPS, BF handled same as prior year | YE
MWG response received re AR changes | YE
MWG response received re R-WI changes | YE
Convey MWG request for style changes, if any, to program staff | YE
Take count of reports left from two years ago | YE
SEPTEMBER of 2013
Directors photo provided to YE | TF
Lithoprint quote received | YE
EXG quote received | YE
Prepare AR & R- WI budgets; to TF | YE
Request cover samples from printer | YE
Receive cover samples | YE
OCTOBER of 2013
Determine quantity of AR | TF/YE
Determine quantity of R-WI | TF/YE
Determine quantity of President enclosure cards | TF
Determine cover stock & color | TF/YE
Determine Inside stock & color | TF/YE
Receive style changes from Program staff for AR, if any | YE
Receive style changes from Program staff for R-WI, if any | YE
NOVEMBER of 2013
Ask TF to request updated mail lists (GMC, DF, MMAC) | YE
Request sector descrip text changes from program staff | YE
Provide staff photo to YE | TF
Staff photo received and placed into AR | YE
Staff photo received and placed into R-WI | YE
Ask MWG: cover letter w/WI Rept (encl. Sample) | YE
AR text and style changes completed | YE
R-WI text and style changes completed | YE
Grants list to program staff for editing of descriptions | YE
OR Use descriptions already on website from MH | YE
Sector description text changes to YE | PS
Sector description text changes completed | YE
DECEMBER of 2013
Provide web-site list of grants to YE | MEH
Updated mail lists to YE | TF
Update GMC, DF, MMAC mail lists in E-Tapestry | YE
Run report & export grants from Gifts | YE
Format exported lists for AR | YE
Format exported lists for R-WI | YE
Run Gifts mailing list | YE
Run E-Tapestry mailing list | YE
Combine Gifts and e-Tapestry mail lists | YE
Provice AR mail list for DK to route to program staff | YE
Enter grants into AR document | YE
Enter grants into R-WI document | YE
Run grant tape totals; check all grants entered on AR | YE
Run grant tape totals; check all grants entered on R-WI | YE
Provide AR draft to Program Staff | YE
Provide R-WI draft to Program Staff | YE
Staff changes on AR returned to YE | PS
Staff changes on R-WI returned to YE | PS
Program Staff changes made to AR | YE
Program Staff changes made to R-WI | YE
Provide AR draft to MEH | YE
AR draft returned to YE | MEH
MEH changes to AR completed | YE
Run grant tape total; check all grants entered on AR | YE
Run grant tape total; check all grants entered on R-WI | YE
Prepare reconciliation of grants to financial statement | YE
Provide AR draft to CF w/reconciliation to financial stmt | YE
AR draft returned to YE | CF
Changes to AR completed | YE
Provide AR draft to MWG | YE
AR draft returned to YE | MWG
MWG changes to AR completed | YE
Provide R-WI draft to MEH | YE
R-WI draft returned to YE | YE
MEH changes to R-WI completed | YE
Provide R-WI draft to CF w/tape totals attached | YE
R-WI draft returned to YE | CF
Changes to R-WI completed | YE
Provide R-WI draft to MWG | YE
R-WI draft returned to YE | MWG
MWG changes to R-WI completed | YE
JANUARY of 2014
Select foil and ink colors | TF/YE
Return mail list changes to YE | DK
Recommended mail list changes to MWG | YE
Mail list changes returned to YE | MWG
AR mail list changes completed | YE
R-WI mail list prepared (pulled from AR mail list) | YE
R-WI mail list to MWG for review | YE
R-WI mail list returned to YE | MWG
R-WI mail list completed | YE
Send AR mail list to printer | YE
Send R-WI mail list to printer | YE
President's letter for R-WI to YE (if needed) | MWG
Draft of President's letter completed | YE
Final of President's letter completed | YE
Letters printed in-house for printer to enclose | YE
Provide final AR draft to MWG/CF/DPS/TF for sign off (ex: FiHi) | YE
Provide final R-WI draft to MWG/CF/DPS/TF for sign off | YE
AR draft returned to YE | VPs
R-WI draft returned to YE | VPs
Changes to AR completed | YE
Changes to R-WI completed | YE
FEBRUARY of 2014
AR mail list sent to printer | YE
R-WI mail list sent to printer | YE
Financial Highlights to YE (as soon after Feb. brd mtg as possible) | MLH
Financial highlights page prepared | YE
Draft of financial highlights to MLH for review | YE
Changes to financial highlights to YE | YE
Changes to financial highlights completed | YE
Draft of financial highlights to CF for review & sign off | YE
Any changes to financial highlights to YE | CF
Changes to financial highlights completed | YE
Draft of financial highlights to MWG for approval | YE
Financial highlights returned to YE | MWG
Financial highlights completed in AR | YE
MARCH OF 2014
AR packaged by software | YE
R-WI packaged by software | YE
AR CD prepared for printer | YE
R-WI CD prepared for printer | YE
Print color copy of AR for printer | YE
Print color copy of R-WI for printer | YE
CD of AR sent to printer w/color copy print-out | YE
CD of R-WI sent to printer w/color copy print-out | YE
President's letter sent to printer | YE
AR proof received | YE
AR proof reviewed | YE
AR proof reviewed, signed off | CF
AR proof reviewed, signed off | DPS
R-WI proof received | YE
R-WI proof reviewed | YE
R-WI proof reviewed, signed off | CF
R-WI proof reviewed, signed off | DPS
Changes to AR returned to printer (if any) | YE
Changes to R-WI returned to printer (if any) | YE
New proofs received & reviewed | YE
AR proof acceptance form signed and returned | YE
R-WI proof acceptance form signed and returned | YE
20 AR received | LP
20 R-WI received | YE
AR mailed by printer | YE
R-WI mailed by printer | LP
Remainder AR delivered to Fdn. | YE
Remainder R-WI delivered to Fdn. | LP
Copy to each staff member | LP
Email to staff re: copy of the reports left on their desk | YE
Invoice received | YE