Responsible	Due	Date

Item		Party	Date	Completed

Contact printer to verify availability	Yvone	12/31/04	12/17/04

Contact Whitaker Works to verify availability	Terri	12/31/04	1/4/05

Reports (3) created alphabetically in Gifts to RTF file	Yvonne	1/7/05	1/7/05

Hard copy (of full AR)    to Dan/Dianne to edit 	Yvonne	1/7/05	12/29/04

project descriptions

Edit project descriptions	Dan/Dianne	1/7/05	1/4/04

Transfer edited descriptions to alpha list	Yvonne	1/7/05	1/7/05

E-mail Gifts reports (3) files to Susan in Word	Yvonne	1/12/05	1/7/05

Send hard copy with edits to Susan	Yvonne	1/12/05	1/7/05

Re-write last year’s Letter to Community	Mike	1/14/05

Send any revisions to intro section to Susan	Terri	1/14/05

(Board & staff listing, table of contents, letter to

community, history, future, policies, procedures)

Compare/identify organizations needing logos	Susan	1/19/05

Obtain missing logos	Susan	1/27/05

Draft of 3 different enclosure letters to MWG	Susan	2/2/05

(Local grantees, Leaders, Media)

Complete formatting/editing of intro section 	Susan	2/4/05

Choose cover design, colors, and texture style	Mike G./Terri/Susan	2/4/05

(Complimentary to full AR; color reversed?)

Finalize selections for mailing lists	 Mike G./Terri/Yvonne	2/4/05

(Grantees, media, local leaders)

Prepare mailing lists in Excel	Yvonne	2/7/05

Decide how many local reports to 	Mike, Yvonne, Terri	2/7/05

be printed & ordered (600 last year)

Formatting and editing of grants listing	Susan	2/7/05

Approve enclosure letters	Mike	2/7/05

First draft of report to Terri/Yvonne for proofing	Susan	2/8/05

Send mailing lists to Susan (for letters)	Yvonne	2/8/05

Send mailing lists to printer	Yvonne	2/8/05

Responsible	Due	Date

Item		Party	Date	Completed

Proofread draft (and run tape total of grants) 	Yvonne/Terri	2/9/05

Changes back to Susan	Terri/Yvonne	2/9/05

Second draft to Terri/Yvonne	Susan	2/11/05

Complete proof-reading of second draft	Yvonne/Terri	2/11/05

President’s approval of draft w/changes noted	Mike G.	2/11/05

Final changes to Susan	Terri	2/11/05

Proof final changes and approve report	Terri	2/11/05

Send files to Lithoprint	Susan	2/11/05

Printed enclosure letters to Mike G./Terri (to copy)	Susan	2/14/05

Complete proof-reading of printer’s proofs 	Mike G./Terri/Yvonne	2/18/05

Fax printer’s proof approval form 	Susan	2/18/05

Draft Local Report available (for Board?)	Mike G./Terri	2/22/05

(Possibly in final format)

Send file to Christina (to use on web site)	Susan	3/31/05

First box of bound reports expected	LithoPrint	3/31/05

Mail Reports (bulk mail)	LithoPrint	3/31/05

Mail Report to Directors	Terri	4/4/05

Update web site with 2004 Report to Wisconsin 	Christina	7/1/05