| ITEM | PERSON | DATE | NOTES | DONE |
| --- | --- | --- | --- | --- |
| Contact Christina to verify availability | TF | 09/15/08 |  | 9/15/08 |
| Contact LithoPrint (LP) to verify availability | YE | 09/15/08 |  | 9/22/08 |
| Contact LP to request quote | YE | 09/30/08 | 10/9 rec’d | 9/22/08 |
| Bradley Prizes write-up completed; to YE | DJS | 09/30/08 | 9/3 e-DJS | 9/5/08 |
| Symposium write-up completed; to YE | MH | 09/30/08 |  | 11/11/08 |
| Determine BP & Symp. pictures to use | YE/TF/MWG | 09/30/08 | 11/11-questions | 11/12/08 |
| Send pictures to CS | YE | 09/30/08 |  | 11/12/08 |
| Send Prizes write-up to CS | YE | 09/30/08 |  | 09/22/08 |
| Send updated Prizes & Symp. Write-ups to CS | YE | 09/30/08 |  | 11/11/08 |
| Request cover samples from LP | YE | 10/01/08 |  | 10/6/08 |
| Determine quantity of AR | YE/TF | 10/31/08 | ‘07=1500//08=1500 | 11/11/08 |
| Determine # of pictures to use | YE/TF | 10/31/08 |  | 11/11/08 |
| Determine cover stock & color | YE/TF | 10/31/08 | Navy | 11/11/08 |
| Determine inside stock & color | YE/TF | 10/31/08 | Same as 07 | 11/11/08 |
| Select foil and ink colors | YE/TF | 10/31/08 | Gold | 11/11/08 |
| Est. number of pages needed compared to prior year | YE/TF | 10/31/08 |  | 11/11/08 |
| Confirm GCCs & BPS grants not included; BFs same | YE/TF | 10/31/08 |  | 11/11/08 |
| Confirm sector & intro texts | YE/TF | 10/31/08 |  | 11/11/08 |
| Determine any style changes or additional information to be included | YE/TF | 10/31/08 |  | 11/11/08 |
| If no changes needed, ask CS to start Intro section | YE | 10/31/08 |  | 11/12/08 |
| Determine how many enclosure cards are needed | TF | 10/31/08 | Have 990 | 03/24/09 |
| Contact LP with paper/cover selections, etc. | YE | 11/07/08 |  | 11/12/08 |
| Changes to intro section to CS (if needed) | YE | 11/30/08 |  | ----- |
| 1st draft of BP and Symp to YE | CS | 12/01/08 |  | 12/01/08 |
| 1st draft of intro section to YE | CS | 12/01/08 |  | 01/02/09 |
| Director photo provided to YE | TF | 12/01/08 | Retake req. | 02/02/09 |
| Directors’ photo to CS | YE | 12/02/08 |  | 03/03/09 |
| Run Gifts report of grants for website | DD | 12/05/08 |  | 12/15/08? |
| Edit descriptions for website | DPS,MH,DJS,DD | 12/08/08 |  | 01/31/09 |
| Proof descriptions for website | DD | 12/10/08 |  | 01/15/09 |
| Reconcile website with pre-audit grant totals | MLH | 03/06/09 |  | 03/05/09 |
| Provide webmaster with 2008 grants listing | MH | 12/10/08 |  | 1/21/09 |
| Send web electronic files & printout of grant files to YE | MH | 12/12/08 | .doc or .rtf | 1/21/09 |
| Send grant files to CS, with instructions | YE | 12/15/08 |  | 1/21/09 |
| Send Keiser grant list to CS | YE | 12/17/08 |  | 12/22/08 |
| Final intro section to YE | CS | 12/19/08 |  | 03/16/09 |
| Web v. AR sector descriptions differ – which to use? | MWG/TF | 01/06/09 |  | 02/20/09 |
| 1st draft of grants listing to YE | CS | 01/15/09 |  | 03/06/09 |
| Get updated GMC, DF, MMAC mailing lists | TF | 01/15/09 |  | 02/02/09 |
| Proof 1st draft of grants listing; run tape total | YE | 01/18/09 |  | 03/06/09 |
| Changes to grants listing to CS | YE | 01/20/09 |  | 03/06/09 |
| Update GMC & MMAC mailing lists in ACT | YE | 01/27/09 |  | 02/26/09 |
| Updated draft of grants listing to YE | CS | 01/30/09 |  | 03/16/09 |
| Return grants listing changes to CS | YE | 02/02/09 |  | 03/17/09 |
| Send AR mailing list to printer (remove titles) | YE | 02/04/09 |  | 03/24/09 |
| Continue proofing and changes | YE/CS | 02/4-13/09 |  | 3/18/09 |
| Proofing of grants and intro drafts completed | YE/CS | 02/13/09 |  | 3/17/09 |
| Entire draft to MWG, DPS, CF, TF, MH, RG | YE | 02/16/09 |  | 03/17/09 |
| Compare AR draft to website | YE | 2/16/09 |  | 2/11/09 |
| Compile changes or approvals & send to CS | YE | 02/20/09 |  | 3/11/09 |
| Financial highlights ready? | MLH | 03/10/09 |  | 3/12/09 |
| Send financial highlights to CS | YE | 02/24/09 |  | 3/12/09 |
| Draft of financial highlights to YE | CS | 02/25/09 |  | 3/16/09 |
| Draft of financial highlights to CF/MLH | YE | 02/25/09 |  | Changes |
| Changes to financial highlights to YE | MLH | 02/26/09 |  | 3/17/09 |
| Changes to financial highlights to CS | YE | 02/26/09 |  | 3/17/09 |
| Updated draft of entire report to distribute to MWG, DPS, CF, TF, MH, (D&T 3/24) | YE | 02/27/09 |  | 3/18/09 |
| Return recommended changes to YE | MWG, DPS, CF, TF, MH, MLH, RG | 02/20/09 3/23/09 |  | 3/23/09 |
| Ask MWG if he wants a cover letter sent with WI Rept | TF | 03/01/09 | yes | 4/6/09 |
| Verify postage in mail account; add if needed | AH | 03/01/09 |  | 03/24/09 |
| Get media list from Mueller Com for MKE & MAD for WI R. | TF | 03/06/09 | News, mags, talks | 3/30/09 |
| Send WI Report mail list to LP (no titles); Confirm quantity | YE | 03/09/09 | ‘07=1500 ‘08=1200 | 5/7/09 |
| Final AR draft to YE | CS | 03/10/09 |  | 03/24/09 |
| Contact CS if it’s a go or not; review changes, if any | YE | 03/10/09 |  | 03/24/09 |
| Send file and hard copy to LP | CS | 03/11/09 |  | 03/25/09 |
| Provide WI report grant info to CS | YE | 03/11/09 |  | 03/06/09 |
| Start WI Report using AR’s Legacy sector items | CS | 03/12/09 |  | 03/24/09 |
| Send other sectors’ local grants & p.1 $ changes to CS | YE | 03/13/09 |  | 3/13/09 |
| Receive and proof printers proof for AR | YE | 03/19/09 |  | 4/2/09 |
| Sign approval form; indicated changes; return to LP | YE | 03/20/09 |  | 4/6/09 |
| Approve sample of embossed cover | YE | 03/20/09 |  | 4/9/09 |
| 1st draft of WI Report to YE | CS | 03/26/09 |  | 4/28/09 |
| Advance copies (30 Annual Reports) to YE for MWG | LP | 03/27/09 |  | 4/22/09 |
| Changes to WI Report to CS | YE | 03/30/09 |  | 4/29/09 |
| Annual Reports mailed | LP | 03/31/09 |  | 4/24/09 |
| Updated draft of WI Report to YE | CS | 04/02/09 |  | 4/29/09 |
| Updated draft of WI Report to distribute to MWG, DPS, CF, TF, MH, MLH | YE | 04/03/09 |  | 4/29/09 |
| WI Report changes returned to YE 5/1-Rec’d: CF,MLH,DPS;MWG,TF | MWG, DPS, CF, TF, MH, MLH | 04/07/09 5/6/09 |  | 5/1/9 |
| Compile and send WI Report changes to CS, if any | YE | 04/08/09 |  | 5/1/9 |
| Final draft to YE | CS | 04/10/09 |  | 5/6/9 |
| Verify WI Report grant totals on website with post-audit numbers | MLH | 04/10/09 |  | 5/1/9 |
| Contact CS if it’s a go or not; review changes, if any | YE | 04/10/09 |  | 5/6/9 |
| Send file and hard copy to printer | CS | 04/13/09 |  | 5/7/09 |
| Receive and proof printer’s proof | YE | 04/20/09 | 5/15 in progress |  |
| Sign approval form; indicated changes; return to LP | YE | 04/21/09 |  |  |
| Report to Wisconsin mailed | LP | 04/30/09 |  |  |
| Post publication: verify totals of AR & web with post-audit numbers | MLH | 04/30/09 |  |  |

/tmp/in/input.doc               							Updated 05/19/09