| ITEM | PERSON | EST DATE | NOTES | DONE |
| --- | --- | --- | --- | --- |
| Request new sector texts | YE/TF | 07/31/09 |  | 07/30/09 |
| Contact LithoPrint to verify availability & request quote | YE | 08/28/09 |  |  |
| Request BP & Symp write-ups from DJS/MH | YE | 08/28/09 |  |  |
| Quote received by YE | LP | 09/11/09 |  |  |
| Bradley Prizes write-up completed; to YE | DJS | 09/18/09 |  |  |
| Symposium write-up completed; to YE | MH | 09/18/09 |  |  |
| Determine BP & Symp. pictures to use | YE/TF/MWG | 09/30/09 |  |  |
| Confirm GCCs, BPS, BFs handled same as prior year | YE/TF | 09/30/09 |  |  |
| New program area texts, style to YE | DPS/MWG | 09/30/09 |  |  |
| Request cover samples from LP | YE | 09/30/09 |  |  |
| Receive cover samples | LP | 10/14/09 |  |  |
| Determine quantity of AR | YE/TF | 10/30/09 | ‘08=1500 |  |
| Determine cover stock & color | YE/TF | 10/30/09 | Silver |  |
| Determine inside stock & color | YE/TF | 10/30/09 | Same |  |
| Select foil and ink colors | YE/TF | 10/30/09 | Gold, Navy? |  |
| Determine how many enclosure cards are needed | TF | 10/30/09 |  |  |
| Director photo provided to YE | TF | 11/02/09 |  |  |
| Request updated GMC, DF, MMAC mailing lists | TF | 11/02/09 |  |  |
| Contact LP with paper/cover selections, etc. | YE | 11/06/09 |  |  |
| Run Gifts report for web site, give to DPS, MH, DJS | DD | 11/20/09 |  |  |
| Edit grant descriptions for website & return to DD | DPS/MH/DJS | 12/09/09 |  |  |
| Provide edited grant descriptions to YE | DD | 12/09/09 |  |  |
| Provide webmaster with 2009 grants listing | MH | 12/09/09 |  |  |
| Receive GMC, DF, MMAC mailing lists | YE | 12/14/09 |  |  |
| Reconcile website with pre-audit grant totals | MLH | 12/30/09 |  |  |
| Update GMC & MMAC mailing lists in ACT | YE | 12/30/09 |  |  |
| Grant entries completed; run tape total | YE | 01/11/10 |  |  |
| Provide 1st AR draft to TF/DPS/MWG/CF | YE | 01/11/10 |  |  |
| 1st proof of grants listing completed & returned to YE | TF/DPS/MWG/CF | 01/18/10 |  |  |
| Continue proofing and changes | YE/DPS/MWG/CF/TF | 1/18-1/25 |  |  |
| Prepare AR mailing list | YE | 01/25/10 |  |  |
| Send AR mailing list to printer (remove titles) | YE | 01/29/10 |  |  |
| Changes of grants and intro drafts completed | YE | 01/31/10 |  |  |
| Start WI Report using AR’s new sector items | YE | 02/01/10 |  |  |
| Compare AR draft to website | YE | 02/02/10 |  |  |
| Make other sectors’ local grants & p.1 $ changes | YE | 02/05/10 |  |  |
| Draft of financial highlights to YE | MLH | 02/05/10 |  |  |
| Draft of financial highlights to CF/MLH | YE | 02/08/10 |  |  |
| Changes to financial highlights to YE | MLH | 02/10/10 |  |  |
| Entire “final” draft to MWG, DPS, CF, TF, MH, RG, DT | YE | 02/19/10 |  |  |
| Return recommended changes to YE | MWG, DPS, CF, TF, MH, MLH, RG, D&T | 02/26/10 |  |  |
| Ask MWG if he wants a cover letter sent with WI Rept | TF | 03/01/10 |  |  |
| Verify postage in mail account for both; add if needed | SR | 03/01/10 |  |  |
| Request media list from Mueller Com for MKE & MAD for WI Report | TF | 03/01/10 | News, mags, talks |  |
| Final AR changes done | YE | 03/05/10 |  |  |
| Send file and hard copy to LP after approvals | YE | 03/05/10 |  |  |
| Updated draft of WI Report to distribute to MWG, DPS, CF, TF, MH, MLH | YE | 03/05/10 |  |  |
| Confirm quantity with LP | YE | 03/09/10 | 08=1200; 09= |  |
| Send WI Report mail list to LP (no titles) | YE | 03/12/10 |  |  |
| Receive and proof printers proof for AR | YE | 03/12/10 |  |  |
| WI Report changes returned to YE | MWG, DPS, CF, TF, MH, MLH | 03/15/10 |  |  |
| Sign AR approval form; indicated changes; return to LP | YE | 03/15/10 |  |  |
| Changes made to WI report | YE | 03/18/10 |  |  |
| Final WI draft to TF, MWG, DPS | YE | 03/19/10 |  |  |
| Approve sample of embossed cover | YE | 03/20/10 |  |  |
| Verify WI Report grant totals on website with post-audit numbers | MLH | 03/24/10 |  |  |
| WI Report changes to YE | TF, MWG, DPS | 03/25/10 |  |  |
| Advance copies (30 Annual Reports) to YE for MWG | LP | 03/26/10 |  |  |
| Annual Reports mailed | LP | 03/31/10 |  |  |
| Send WI report file and hard copy to printer | YE | 04/04/10 |  |  |
| Receive and proof printer’s proof of WI report | YE | 04/12/10 |  |  |
| Sign approval form; indicated changes; return to LP | YE | 04/16/10 |  |  |
| Report to Wisconsin mailed | LP | 04/30/09 |  |  |
| Post publication: verify totals of AR & web with post-audit numbers | MLH | 04/30/09 |  |  |

/tmp/in/input.doc               							Updated 08/04/09