| ITEM | PERSON | EST DATE | NOTES | DONE |
| --- | --- | --- | --- | --- |
| Request BP & Symp write-ups from DJS/MH | YE | 08/13/09 |  | 8/13/09 |
| Request program area & text description changes | TF/YE | 08/13/09 |  | 8/13/09 |
| Confirm GCCs, BPS, BFs handled same as prior year | TF/YE | 08/13/09 |  | 8/13/09 |
| Bradley Prizes write-up completed; to YE | DJS | 08/27/09 |  | 8/13/09 |
| Symposium write-up completed; to YE | MH | 08/27/09 |  | 8/13/09 |
| AR & WI text and style changes to YE | MWG/DPS | 09/02/09 |  | 12/10/09 |
| Distribute first 3 qts grants list for editing | DK | 09/02/09 |  | ----- |
| Text and style changes completed | YE | 09/11/09 |  | 12/10/09 |
| Contact LithoPrint to verify availability & request quote | YE | 09/11/09 |  | 9/3 |
| Contact EGX to request quote | YE | 09/11/09 |  | 8/25 |
| Draft to MH | YE |  |  | 12/10 |
| Return edited grant descriptions to YE | DPS, DJS, MH | 09/16/09 |  |  |
| EGX quote received by Y E | YE | 09/18/09 |  | 9/25/09 |
| LP quote received by YE | LP | 09/18/09 |  | 9/18/09 |
| Request cover samples from LP | YE | 09/23/09 |  | 10/15/09 |
| Receive cover samples | LP | 09/30/09 |  | 10/20/09 |
| Determine BP & Symp. pictures to use | MWG/TF/YE | 09/30/09 |  | 8/17/09 |
| Provide YTD 3rd qt draft for review to DPS, MH, TF | YE | 09/30/09 |  | ----- |
| Ask MWG if he wants a cover letter sent with WI Rept | TF | 10/01/09 |  |  |
| Determine quantity of AR and WI Report | TF/YE | 10/15/09 | ‘08=1500/1200 | 10/27 |
| Determine cover stock & color | TF/YE | 10/15/09 |  | 10/27 |
| Determine inside stock & color | YE/TF | 10/15/09 |  | 10/27 |
| Draft of WI Rept cover letter to YE (if needed) | MWG | 10/15/09 |  |  |
| YTD 3rd qt review complete & returned to YE | DPS/MH/TF | 10/20/09 |  | ----- |
| Cover letter prepared; draft to MWG (if needed) | YE | 10/20/09 |  |  |
| Determine how many enclosure cards are needed | TF | 10/30/09 |  |  |
| Contact LP with selections, & request foil samples | YE | 10/30/09 |  | 10/15/09 |
| Request updated GMC, DF, MMAC mailing lists | TF | 11/02/09 |  |  |
| Select foil and ink colors | TF/YE | 11/09/09 |  |  |
| WI Rept cover letter merged & printed (if needed) | YE | 11/10/09 |  |  |
| Receive GMC, DF, MMAC mailing lists | YE | 11/16/09 |  |  |
| Update GMC & MMAC mailing lists in ACT | YE | 11/30/09 |  |  |
| Distribute 4th qt grants list for editing of descriptions | DK | 11/30/09 |  | ----- |
| Director photo provided to YE | TF | 11/30/09 |  | 11/15/09 |
| Return edited grant descriptions to YE | DPS, DJS, MH | 12/07/09 |  | ----- |
| Enter 4th qt grants into AR document | YE | 12/07/09 |  | 12/10/09 |
| Enter 4th qt grants into cumulative document for web | YE | 12/08/09 |  | ----- |
| Enter 4th qt grants into WI report document | YE | 12/09/09 |  |  |
| Review/proof cumulative grant list for webmaster | MH | 12/09/09 |  | done |
| Provide 1st draft to MWG/DPS/CF/TF/MH-only | YE | 12/09/09 |  | 12/21/09 |
| Provide unaudited financial highlights to YE | CF/MLH | 12/09/09 |  |  |
| Request media list from Mueller Com for MKE & MAD for WI Report | TF | 12/09/09 | News, mags, talks |  |
| Send cumulative AR grant list to webmaster | MH | 12/13/09 |  |  |
| Financial highlights entered; draft to CF/MLH | YE | 12/13/09 |  |  |
| Run grant tape total; check all grants entered | YE | 12/17/09 |  | 12/18/09 |
| Receive media lists | YE | 12/21/09 |  |  |
| Grant listing completed on website | MH | 12/30/09 |  |  |
| Approve sample of embossed cover | YE | 01/05/10 |  |  |
| Compare AR draft to website | MLH/YE | 01/05/10 |  |  |
| Verify postage in mail account for both; add if needed | SR | 01/06/10 |  |  |
| Reconcile website with pre-audit grant totals | MLH | 01/06/10 |  |  |
| AR mailing list prepared | YE | 01/06/10 |  |  |
| WI Report mail list prepared | YE | 01/07/10 |  |  |
| Final draft to MWG, DPS, CF, TF, MH, MLH, RG, DT | YE | 01/07/10 |  |  |
| Review/approve mail list | MWG/TF | 01/07/10 |  |  |
| Send AR & WI mailing lists to printer (remove titles) | YE | 01/10/10 |  |  |
| Return recommended AR changes to YE | MWG, DPS, CF, TF, MH, MLH, RG, D&T | 01/14/10 |  |  |
| Final WI draft to MWG, DPS, CF, TF, MH, RG, DT | YE | 01/14/10 |  |  |
| Send AR file and hard copy to LP | YE | 01/16/10 |  |  |
| WI Report changes returned to YE | MWG, DPS, CF, TF, MH, MLH | 01/21/10 |  |  |
| Send WI report file and hard copy to printer | YE | 01/22/10 |  |  |
| Receive and proof printers proof for AR | YE | 01/23/10 |  |  |
| Sign AR approval form; indicated changes; return to LP | YE | 01/24/10 |  |  |
| Receive and proof printers proofs for WI report | YE | 02/02/10 |  |  |
| Sign WI approval form; indicate changes; return to LP | YE | 02/03/10 |  |  |
| Advance copies (30 Annual Reports) to YE for MWG | LP | 01/31/10 |  |  |
| Annual Reports mailed | LP | 01/31/10 |  |  |
| Report to Wisconsin mailed | LP | 02/10/10 |  |  |
| Verify AR & WI Report grant totals with website and post-audit numbers | MLH | 02/28/10 |  |  |

Updated 12/21/09