| ITEM | PERSON | EST DATE | NOTES | DONE |
| --- | --- | --- | --- | --- |
| Ask if any style or text changes to the AR | YE | 6/30 |  |  |
| Provide style or text changes for AR to YE | MWG | 7/31 |  |  |
| Ask if any style or text changes to the WI-R | YE | 7/15 |  |  |
| Provide style or text changes for WI-R to YE | MWG | 8/15 |  |  |
| Text and style changes completed for AR | YE | 8/15 |  |  |
| Text and style changes completed for WI-R | YE | 8/31 |  |  |
| See TF re: bids for printer of AR | YE | 7/20 |  |  |
| Contact other printers to request quote | YE | 7/31 |  |  |
| Contact LithoPrint to verify availability & request quote |  | 7/31 |  |  |
| Other printer quotes received |  | 8/15 |  |  |
| LP quote received by YE | LP | 8/15 |  |  |
| Balance AR with 12/31 numbers | YE |  |  |  |
| Run tape total of AR grants | YE |  |  |  |
| Run tape total of WI-R grants | YE |  |  |  |
| Run WI-R grants report from Gifts | YE |  |  |  |
| Request BP & Symp write-ups from DJS/MH | YE |  |  |  |
| Run AR Grants awarded report from Gifts | YE |  |  |  |
| Bradley Prizes write-up completed; to YE | DJS |  |  |  |
| Symposium write-up completed; to YE | MH |  |  |  |
| Director photo provided to YE | TF |  |  |  |
| Request cover samples from LP | YE |  |  |  |
| Receive cover samples | LP |  |  |  |
| Determine BP & Symp. pictures to use | MWG/TF/YE |  |  |  |
| Determine quantity of AR and WI Report | TF/YE |  | ‘08=1500/1200 |  |
| Determine cover stock & color | TF/YE |  |  |  |
| Determine inside stock & color | TF/YE |  |  |  |
| Select foil and ink colors | TF/YE |  |  |  |
| Determine how many enclosure cards are needed | TF |  |  |  |
| Contact LP with paper/cover selections, etc. | YE |  |  |  |
| Request Mueller media list for WI-R | TF |  |  |  |
| Request updated GMC, DF, MMAC mailing lists | TF |  |  |  |
| Ask MWG if he wants a cover letter sent with WI Rept; provide last year’s as sample | TF |  |  |  |
| Receive GMC, DF, MMAC mailing lists | YE |  |  |  |
| Update GMC, DF, MMAC mailing lists | YE |  |  |  |
| AR draft mailing list prepared & distributed to DK for circulation to P.S. | YE |  |  |  |
| WI-R draft mail list prepared & distributed to DK for circulation to P.S. | YE |  |  |  |
| AR draft mailing list to MWG | DK |  |  |  |
| WI-R draft mailing list to MWG | DPS, DJS, MH |  |  |  |
| Enter 2010 grants into AR document | YE |  |  |  |
| Provide AR draft to DK for distribution to P.S. | YE |  |  |  |
| Return AR draft to YE with changes to be made | MWG/DPS/CF/MH/TF |  |  |  |
| Provide WI-R draft to DK for distribution to P.S. | YE |  |  |  |
| Return WI-R draft to YE with changes to be made | MWG/DPS/CF/MH/TF |  |  |  |
| Review/proof cumulative grant list for webmaster | MH |  |  |  |
| Provide financial highlights to YE | CF/MLH |  |  |  |
| Send AR grant list to webmaster | MH |  |  |  |
| Financial highlights entered; draft to CF/MLH | YE |  |  |  |
| Run grant tape total; check all grants entered | YE |  |  |  |
| Receive media lists | YE |  |  |  |
| Return AR mail list changes to YE | MWG/DPS |  |  |  |
| Return WI-R mail list changes to YE |  |  |  |  |
| Verify postage in mail account for both; add if needed | SR |  |  |  |
| Grant listing completed on website | MH |  |  |  |
| Approve sample of embossed cover | YE |  |  |  |
| Compare AR draft to website | MLH/YE |  |  |  |
| Reconcile website with pre-audit grant totals | MLH |  |  |  |
| Final draft to MWG, DPS, CF, MH, TF, RG, DT | YE |  |  |  |
| Send AR mailing list to printer (remove titles) | YE |  |  |  |
| Send WI-R mailing list to printer (remove titles) | YE |  |  |  |
| Return recommended AR changes to YE | MWG, DPS, CF, MH, TF, MLH, RG, D&T |  |  |  |
| Final WI draft to MWG, DPS, CF, MH, TF, RG, DT | YE |  |  |  |
| Send AR file and hard copy to printer | YE |  |  |  |
| WI Report changes returned to YE | MWG, DPS, CF, MH, TF, MLH |  |  |  |
| Receive and proof printers proof for AR | YE |  |  |  |
| Sign AR approval form; indicated changes; return to LP | YE |  |  |  |
| Send WI report file and hard copy to printer | YE |  |  |  |
| Advance copies (30 Annual Reports) to YE for MWG | LP |  |  |  |
| Annual Reports mailed | LP |  |  |  |
| Receive and proof printer’s proof of WI report | YE |  |  |  |
| Sign WI approval form; indicated changes; return to LP | YE |  |  |  |
| Report to Wisconsin mailed | LP |  |  |  |
| Verify AR & WI Report grant totals with website and post-audit numbers | MLH |  |  |  |

Updated 09/03/09