## Sheet1
ITEM | PERSON(S) | DATE | DONE | NOTES
Ask MWG if any style or text changes to the AR/WI or WI-R | YE | 2010-06-30 | 2010-08-26
Request BP & Symp write-ups from DJS/MH | YE | 2010-07-01 | 2010-07-15
Bradley Prizes write-up completed; to YE | DJS | 2010-07-30 | 2010-07-19
Symposium write-up completed; to YE | MH | 2010-07-30 | 2010-07-15
Prizes & Symposium pages completed | YE | 2010-08-11 | 2010-07-22
See TF re: bids for printer of AR/WI | YE | 2010-08-13 | 2010-08-11
Contact other printers to request quote | YE | 2010-08-17 | 2010-08-24
Contact LithoPrint to verify availability & request quote | YE | 2010-08-17 | 2010-08-24
Determine BP & Symp. pictures to use & provide to YE | MWG/TF | 2010-09-30
Other printer quotes received | YE | 2010-09-30 | 2010-09-30 | None
LP quote received by YE | LP | 2010-09-30 | 2010-09-28
Director photo provided to YE | TF | 2010-09-30 | 2010-11-11
Request cover samples from printer | YE | 2010-10-02 | 2010-09-29
Provide style, order, or text changes for AR/WI to YE | MWG | 2010-10-05
Text and style changes completed for AR/WI | YE | 2010-10-15
Receive cover samples | YE | 2010-10-15 | 2010-10-13
Give AR/WI text/style changes to MH, TF for proofing | YE | 2010-10-22
Proof text and style changes for AR/WI & return to YE | MH,TF | 2010-10-29
Determine quantity of AR/WI and WI Report | TF/YE | 2010-10-30 | 2010-11-11
Cover choice samples to MWG | YE | 2010-10-20 | 2010-10-18
Determine cover stock & color | TF/YE | 2010-10-30 | 2010-11-11
Determine inside stock & color | TF/YE | 2010-10-30 | 2010-11-11
Select foil and ink colors | TF/YE | 2010-10-30
Determine how many enclosure cards are needed | TF | 2010-10-30
Changes to text and style of AR/WI completed | YE | 2010-11-05
Contact printer with paper/cover selections, etc. | YE | 2010-11-05 | 2010-11-11
Run AR/WI Grants awarded report from Gifts | YE | 2010-12-01
Review/proof cumulative grant list for webmaster | MH | 2010-12-05
Send final AR/WI grant list to webmaster (on-going) | MH | 2010-12-10
Request Mueller media list for WI-R | TF | 2010-12-10
Change AR/WI grant descrip to agree w/web and/or MEH | YE | 2010-12-16
Request updated GMC, DF, MMAC mailing lists | TF | 2010-12-20
Enter 2010 grants into AR/WI document, InDesign CS4 | YE | 2010-12-30
Run tape total of AR/WI grants | YE | 2011-01-02
Ask MWG if he wants a cover letter sent with WI Rept; provide last year’s as sample | TF | 2011-01-03
Prepar reconciliation of AR with 12/31 numbers | YE | 2011-01-04
Provide reconciliation to MH, CF | YE | 2011-01-04
Run tape total of AR grants, balance | YE | 2011-01-06
Run tape total of WI grants, balance | YE | 2011-01-06
Provide AR draft to DK for distribution to P.S. & TF | YE | 2011-01-07
Receive GMC, DF, MMAC mailing lists | YE | 2011-01-10
Update mailing lists | YE | 2011-01-12
WI-R cover letter to YE, if needed | MWG | 2011-01-13
Provide WI-R draft to DK for distribution to P.S. & TF | YE | 2011-01-14
Return recommended AR changes to YE | MWG, DPS, CF, MH, TF, MLH | 2011-01-14
Final AR draft to MWG, DPS, CF, MH, TF, RG, DT | YE | 2011-01-14
Return AR draft to YE with changes to be made | MWG/TF/DPS/MH/CF | 2011-01-15
WI-R cover letter prepared, to MWG for review | YE | 2011-01-15
Update GMC, DF, MMAC mailing lists | YE | 2011-01-17
Verify postage in mail account for both; add if needed | SR | 2011-01-18
Return recommended WI changes to YE | MWG, DPS, CF, MH, TF, MLH | 2011-01-20
AR draft mailing list prepared & distributed to DK for circulation to P.S. | YE | 2011-01-20
Final WI draft to MWG, DPS, CF, MH, TF, RG, DT | YE | 2011-01-21
WI-R draft mail list prepared & distributed to DK for circulation to P.S. | MH,TF | 2011-01-27
Return WI-R draft to YE with changes to be made | MWG, DPS, CF, MH, TF, MLH | 2011-01-28
WI-R final changes to TF, MH for review | YE | 2011-01-31
Final in-house proof completed, to YE | TF, MH | 2011-01-31
Send WI-R to printer w/disc & hard copy | YE | 2011-01-31
Return AR mail list changes to YE | MWG/DPS | 2011-01-31
Approve sample of embossed cover | YE | 2011-01-31
Return WI-R mail list changes to YE | MWG/DPS | 2011-02-03
Run WI grant tape total; check al grants entered | YE | 2011-02-04
Run AR grant tape total; check all grants entered | YE | 2011-02-07
Send WI-R mailing list to printer (remove titles) | YE | 2011-02-07
Receive and proof printer’s proof of WI | YE | 2011-02-08
Send AR/WI mailing list to printer (remove titles) | YE | 2011-02-08
Provide financial highlights to YE | CF/MLH | 2011-02-08
Financial highlights entered; draft to CF/MLH | YE | 2011-02-09
Changes to Financial Highlights to YE | CF/MLH | 2011-02-10
Complete changes to Financial highlights | YE | 2011-02-11
Grant listing completed on website | MH | 2011-02-11
Sign WI approval form; indicated changes; return to LP | YE | 2011-02-11
Sign AR approval form; indicated changes; return to LP | YE | 2011-02-14
Compare AR draft to website | MLH/YE | 2011-02-14
Reconcile website with pre-audit grant totals | MLH | 2011-02-14
Send WI files and hard copy to printer | YE | 2011-02-14
Send AR files and hard copy to printer | YE | 2011-02-20
Report to Wisconsin mailed | YE | 2011-02-22
Advance copies (30 Annual Reports) to YE for MWG | LP | 2011-02-27
PDF version of AR/WI to MH | YE | 2011-02-28
Annual Reports mailed | LP | 2011-03-01
If want mailed by 1/31, need to eliminate Financial Highlights; perhaps say avail on web?