## Sheet1
TASK LIST FOR 2015 ANNUAL & WI REPORTS | BY | DUE | DONE | NOTES
PRIZES AND SYMPOSIUM PAGES AND PHOTOS
Determine Prizes pictures to use and inform RN | TF
Determine Symposium pictures to use and inform RN | MH |  | 2015-12-04
Bradley Prizes write-up to RN | DJS |  | 2015-06-15
Symposium write-up to RN | MH |  | 2015-12-04
BP write-up done in AR-draft | RN
Symp write-up done in AR-draft | RN
Place BP pictures | RN
Place Symposium pictures | RN
BP and symposium pages to DJS, TF and MH for review | RN
If changes, updated pages to editor for proofing/approval | RN
Directors photo provided to RN | TF
Provide staff photo to RN | TF |  | 2015-09-23
FORMAT VERIFICATION
Take count of reports left from two years ago for TF | WB |  | x
Contact Lithoprint to request quote | TF/RN |  | 2015-09-18
Ask MWG if any major style changes to AR | RN |  | 2016-01-12
Bradley Legacy - Capital |  |  | 2016-01-12
Bradley Legacy - Civic Growth & Prosperity |  |  | 2016-01-12
Bradley Legacy - Civic Identity |  |  | 2016-01-12
Bradley Legacy - Education |  |  | 2016-01-12
Bradley Legacy - Family and Society |  |  | 2016-01-12
Civil Society |  |  | 2016-01-12
Education |  |  | 2016-01-12
Law and Society |  |  | 2016-01-12
National Defense and Foreign Policy |  |  | 2016-01-12
Public Discourse |  |  | 2016-01-12
Public Policy Research |  |  | 2016-01-12
Ask MWG if any major style changes to R-WI | RN |  | 2016-01-12
Grantees listed in alpha order with logos |  |  | 2016-01-12
Confirm GCCs, BPS, BF handled same as prior year | RN |  | 2016-01-12
GCC's - do NOT include |  |  | 2016-01-12
Bradley Prize Selector grants - do NOT include |  |  | 2016-01-12
Bradley Fellows - consolidated into one item |  |  | 2016-01-12
MWG response received re AR changes | RN |  | 2016-01-12
MWG response received re R-WI changes | RN |  | 2016-01-12
Convey MWG style changes, if any, to DPS | RN |  | 2016-01-12
Receive style changes from Program staff for AR, if any | RN |  | 2016-01-12
Receive style changes from Program staff for R-WI, if any | RN |  | 2016-01-12
Ask MWG - cover letter w/WI Rept (encl. sample)? | RN |  | 2016-01-12
Verify all logos for R-WI are current | RN
PRINTER LOGISTICS
Request quote from printer for next year's budget | TF/RN |  | 2015-09-18
Lithoprint quote received | TF/RN |  | 2015-09-18
Prepare AR & R- WI budgets | TF/RN |  | x
Request cover samples from printer | TF/RN
Receive cover samples | TF/RN
Determine quantity of AR | TF/RN
Determine quantity of R-WI | TF/RN
Determine quantity of President enclosure cards | TF/RN |  |  | May have enough from previous years, check count
Determine cover stock and color | TF/RN
Determine inside stock and color | TF/RN
Select foil and ink colors | TF
President's letter for R-WI to RN (if needed) | MWG |  |  | No letter in 2015 for the 2014 report
Draft of President's letter completed | RN
Final of President's letter completed | RN
Letters printed in-house for printer to enclose | RN
MAILING LISTS
Ask TF to request updated mail lists (DF, GMC, MMAC) | RN |  | x
Updated DF, GMC, MMAC mail lists to RN | TF |  | 2015-09-09
DF, GMC, MMAC mail lists updated in eTapestry | RN |  | 2015-09-01
Run eTapestry mailing list | RN |  | 2015-12-07
Run Gifts mailing list - grantees from last 2 years | RN |  | 2015-12-07
Combine Gifts and eTapestry mail lists | RN |  | 2015-12-07
Circulate AR and R-WI mail lists to Program staff for review | RN | 2016-01-07 | 2016-01-07 | Due Back to RN by 1/28/16
Separate list for R-WI pulled from AR mail list
Return mail list recommended changes to RN | Program | 2016-01-28 | 2016-01-28
Recommended mail list changes to MWG for review | RN | 2016-02-05 | 2016-02-05
Approved mail list changes returned to RN | MWG | 2016-02-05 | 2016-02-05
AR and R-WI mail list changes completed | RN
AR and R-WI lists to MWG for final proofing and approval | RN
AR and R-WI lists returned to RN | MWG/TF
Send AR mail list to printer | RN
Send R-WI mail list to printer | RN
GRANT LISTS AND REVIEW PROCESS
Provide 2015 grants awards report to CF | RK |  | 2016-01-12
Verify totals to grant reconciliation and budget worksheet | CF | 2016-01-15 | 2016-01-13
Provide verified grants awards report to TF and RN | RK | 2016-01-15 | 2016-01-13
Verify program area and sub sectors (manually mark list) | RN & PO | 2016-02-09 | 2016-02-11 | RN follow up with PO with any questions
Return marked list to RK to apply/update codes | RN | 2016-02-12 | 2016-02-11
Provide updated list to CF for review | RN | 2016-02-22 | 2016-02-19
Review updated grants award report; return to RN | CF | 2016-02-26 | 2016-02-19
RN to verify that updated grant changes were made | RN | 3/8/216
Circulate report to PO's to review title vs. AR description | RN | 2016-01-28 | 1/28/206
Return marked copy to RN | Program | 2016-02-09 | 2016-02-09
Provide marked copy to RK for updating | RN | 2016-02-12 | 2016-02-15
Run list by sectors for AR to CF for verification | RK | 2016-02-19 | 2016-02-19
Provide sector list to CF for review | RK | 2016-02-19 | 2016-02-22
Review AR sector list; return to RN | CF | 2016-02-22 | 2016-02-19
Provide list for R-WI to CF for verification | RN | 2016-02-18 | 2016-02-19
Review list for R-WI; return to RN | CF | 2016-02-19 | 2016-02-19
Enter text and photos into InDesign | RN
InDesign printouts for AR and R-WI to CF for verification | RN
Verify each section of AR and R-WI totals match spreadsheet totals | RN | 2016-03-11 |  | Provide location of spreadsheet to CF with printouts (make sure changes in the AR/R2WI match up with the spreadsheets)
Verified printouts for AR and R-WI returned to RN | CF | 2016-03-18
Circulate InDesign printouts to PO's for final review | RN | 2016-03-22
Include prior marked copy to editors
Changes if any returned to RN | Program
Changes made and returned to editor for proofing | RN
Approved copy returned to RN | Program
FINANCIAL HIGHLIGHTS
Financial highlights to RN asap after Feb board meeting | MLH | 2016-02-26 | 2016-02-23
Financial highlights page prepared | RN | 2016-03-04 | 2016-02-23
Draft of financial highlights to MLH for review | RN | 2016-03-04
Changes to financial highlights to RN | MLH | 2016-03-07
Changes to financial highlights completed | RN | 2016-03-07
Updated financial highlights to MLH for proofing and approval | RN | 2016-03-07 |  | if needed
Draft of financial highlights to CF for review and sign off | RN | 2016-03-09
Any changes to financial highlights to RN | CF | 2016-03-11
Changes to financial highlights completed | RN | 2016-03-11
Changes to CF for proofing and approval | RN | 2016-03-11
Draft of financial highlights to MWG for approval | RN | 2016-03-14
Financial highlights returned to RN | MWG | 2016-03-18
Financial highlights completed in AR | RN | 2016-03-21
Provide final AR draft to MWG/DPS/CF/TF for sign off | RN | 2016-03-23
Provide final R-WI draft to MWG/DPS/CF/TF for sign off | RN | 2016-03-23
PRINTER'S PROOF
AR and R-WI uploaded to FTP for printer | RN
President's letter sent to printer | RN
AR and R-WI proofs received | RN
AR and R-WI proofs reviewed by Program, VPs | RN
Changes to AR and R-WI returned to printer (if any) | RN
New copy received and reviewed - Program, VPs | RN
AR and R-WI proof reviewed, signed off | DPS, CF
AR and R-WI proofs reviewed, signed off | MWG
AR and R-WI proof acceptance form signed | TF
Acceptance forms returned to printer for approval to print | RN
FINAL COPY
25 copies of AR and R-WI received | TF/RN
AR and R-WI mailed by printer | Printer
Bulk mail permit used for postage | Printer
Remaining AR and R-WI delivered to Fdn | Printer
Copy to staff - ask MWG 1st about email transmittal | TF/RN
Invoice received | TF/RN
PDF versions emailed to MH for posting on website | RN