## To share
TASK LIST FOR 2014 ANNUAL & WI REPORTS | BY | DONE | NOTES
PRIZES AND SYMPOSIUM PAGES AND PHOTOS
Determine Prizes pictures to use and inform RN | TF | 2015-01-02
Determine Symposium pictures to use and inform RN | MH | x
Bradley Prizes write-up to RN | DJS | 2014-07-10
Symposium write-up to RN | MH | x
BP write-up done in AR-draft | RN
Symp write-up done in AR-draft | RN
Place BP pictures | RN
Place Symposium pictures | RN
BP and symposium pages to DJS, TF and MH for review | RN
If changes, updated pages to editor for proofing/approval | RN
Directors photo provided to RN | TF |  | Shoot scheduled in Feb 2015
Provide staff photo to RN | TF | x
FORMAT VERIFICATION
Take count of reports left from two years ago for TF | WB | 2014-09-05
Contact Lithoprint to request quote | TF/RN | 2014-09-09
Ask MWG if any major style changes to AR | RN | x | No changes
Bradley Legacy - Capital
Bradley Legacy - Civic Growth & Prosperity
Bradley Legacy - Civic Identity
Bradley Legacy - Education
Bradley Legacy - Family and Society
Civil Society
Education
Law and Society
National Defense and Foreign Policy
Public Discourse
Public Policy Research
Ask MWG if any major style changes to R-WI | RN | x | No changes
Grantees listed in alpha order with logos
Confirm GCCs, BPS, BF handled same as prior year | RN | x
GCC's - do NOT include
Bradley Prize Selector grants - do NOT include
Bradley Fellows - consolidated into one item
MWG response received re AR changes | RN | n/a
MWG response received re R-WI changes | RN | n/a
Convey MWG style changes, if any, to DPS | RN | n/a
Receive style changes from Program staff for AR, if any | RN | n/a
Receive style changes from Program staff for R-WI, if any | RN | n/a
Ask MWG - cover letter w/WI Rept (encl. sample)? | RN | x | Confirming no letter
Verify all logos for R-WI are current | RN |  | Collaborate with Program
PRINTER LOGISTICS
Request quote from printer for next year's budget | TF/RN | x
Lithoprint quote received | TF/RN | 2014-09-09
Prepare AR & R- WI budgets | TF/RN | 2014-09-09
Request cover samples from printer | TF/RN | 2014-01-13 | Phone conf w/Lithoprint
Receive cover samples | TF/RN
Determine quantity of AR | TF/RN
Determine quantity of R-WI | TF/RN
Determine quantity of President enclosure cards | TF/RN
Determine cover stock and color | TF/RN
Determine inside stock and color | TF/RN
Select foil and ink colors | TF
President's letter for R-WI to RN (if needed) | MWG | n/a
Draft of President's letter completed | RN | n/a
Final of President's letter completed | RN | n/a
Letters printed in-house for printer to enclose | RN | n/a
MAILING LISTS
Ask TF to request updated mail lists (DF, GMC, MMAC) | RN | x
Updated DF, GMC, MMAC mail lists to RN | TF | x | Jan 5 and 7, 2015
DF, GMC, MMAC mail lists updated in eTapestry | RN | x | Check w/KP re Donor Relations contact updates, if any
Run eTapestry mailing list | RN
Run Gifts mailing list - grantees from last 2 years | RN
Combine Gifts and eTapestry mail lists | RN
Circulate AR and R-WI mail lists to Program staff for review | RN
Separate list for R-WI pulled from AR mail list
Return mail list recommended changes to RN | Program
Recommended mail list changes to MWG for review | RN
Approved mail list changes returned to RN | MWG
AR and R-WI mail list changes completed | RN
AR and R-WI lists to MWG for final proofing and approval | RN
AR and R-WI lists returned to RN | MWG/TF
Send AR mail list to printer | RN
Send R-WI mail list to printer | RN
GRANT LISTS AND REVIEW PROCESS
Provide 2014 grants awards report to CF | RK | x
Verify totals to grant reconciliation and budget worksheet | CF | x
Provide verified grants awards report to TF and RN | RK | x
Verify program area and sub sectors (manually mark list) | RN |  | Compare to prior year's AR; check with PO's to fill in blanks
Return marked list to RK to apply/update codes | RN
Provide updated list to CF for review | RK
Review updated grants award report; return to RK | CF
Provide updated grants awards report to RN | RK
Circulate report to PO's to review title vs. AR description | RN |  | PO's to manually mark desired changes
Return marked copy to RN | Program |  | RN to coordinate circulation and collection of lists
Provide marked copy to RK for updating | RN
Run list by sectors for AR to CF for verification | RK
Provide sector list to CF for review | RK
Review AR sector list; return to RK | CF
Provide list for R-WI to CF for verification | RK
Review list for R-WI; return to RK | CF
Provide list by sectors for AR to RN for InDesign entry | RK
Provide R-WI list to RN for InDesign entry | RK
Enter text and photos into InDesign | RN
InDesign printouts for AR and R-WI to CF for verification | RN
Verified printouts for AR and R-WI returned to RN | CF
Circulate InDesign printouts to PO's for final review | RN
Include prior marked copy to editors
Changes if any returned to RN | Program
Changes made and returned to editor for proofing | RN
Approved copy returned to RN | Program
FINANCIAL HIGHLIGHTS
Financial highlights to RN asap after Feb board meeting | MLH
Financial highlights page prepared | RN
Draft of financial highlights to MLH for review | RN
Changes to financial highlights to RN | MLH
Changes to financial highlights completed | RN
Updated financial highlights to MLH for proofing and approval | RN
Draft of financial highlights to CF for review and sign off | RN
Any changes to financial highlights to RN | CF
Changes to financial highlights completed | RN
Changes to CF for proofing and approval | RN
Draft of financial highlights to MWG for approval | RN
Financial highlights returned to RN | MWG
Financial highlights completed in AR | RN
Provide final AR draft to MWG/DPS/CF/TF for sign off | RN
Provide final R-WI draft to MWG/DPS/CF/TF for sign off | RN
PRINTER'S PROOF
AR and R-WI uploaded to FTP for printer | RN
President's letter sent to printer | RN | n/a
AR and R-WI proofs received | RN
AR and R-WI proofs reviewed by Program, VPs | RN |  | RN circulates and coorindates all review
Changes to AR and R-WI returned to printer (if any) | RN
New copy received and reviewed - Program, VPs | RN |  | RN ciculates and coordinates all review
AR and R-WI proof reviewed, signed off | DPS, CF
AR and R-WI proofs reviewed, signed off | MWG
AR and R-WI proof acceptance form signed | TF
Acceptance forms returned to printer for approval to print | RN
FINAL COPY
25 copies of AR and R-WI received | TF/RN
AR and R-WI mailed by printer | Printer
Bulk mail permit used for postage | Printer
Remaining AR and R-WI delivered to Fdn | Printer
Copy to staff - ask MWG 1st about email transmittal | TF/RN
Invoice received | TF/RN
PDF versions emailed to MH for posting on website | RN