## To share
TIMELINE ANTICIPATED FOR 2014 ANNUAL & WI REPORTS | BY | DONE | VIA | NOTES | NOTES for 2015 Reports | Email, File, Memo, Phone
JUNE
Request BP write-up from DJS | RN | x
Request Symposium write-up from MH | RN | x
Basic template updates, i.e. change year | RN
JULY
Determine BP pictures to use and inform RN | TF | 2015-01-02 | TF
Determine Symposium pictures to use and inform RN | MH
Bradley Prizes write-up to RN | DJS | 2014-07-10 | TF
Symposium write-up to RN | MH
BP write-up done in AR-draft | RN
Symp write-up done in AR-draft | RN
Place BP pictures | RN
Place Symposium pictures | RN
BP and symposium pages to TF and MH for review | RN
If changes, updated pages to TF/MH for proofing/approval | RN
AUGUST
Take count of reports left from two years ago for TF | WB | 2014-09-05 | TF
Contact Lithoprint to request quote | TF/RN | 2014-09-09 | TF
Ask MWG if any major style changes to AR | RN | x |  | No changes
Ask MWG if any major style changes to R-WI | RN | x |  | No changes
Confirm GCCs, BPS, BF handled same as prior year | RN | x
GCC's - do NOT include
Bradley Prize Selectors -
Bradley Fellows - consolidated into one item
MWG response received re AR changes | RN | x
MWG response received re R-WI changes | RN | x
Convey MWG style changes, if any, to DPS | RN | n/a
SEPTEMBER
Directors photo provided to RN | TF |  |  | Shoot scheduled in Feb 2015
Lithoprint quote received | TF/RN | 2014-09-09 | TF
Prepare AR & R- WI budgets | TF/RN | 2014-09-09 | TF
Request cover samples from printer | TF/RN | 2014-01-13 |  | Phone conf w/Lithoprint
Receive cover samples | TF/RN
OCTOBER
Determine quantity of AR | TF/RN
Determine quantity of R-WI | TF/RN
Determine quantity of President enclosure cards | TF/RN
Determine cover stock and color | TF/RN
Determine inside stock and color | TF/RN
Receive style changes from Program staff for AR, if any | RN | n/a
Receive style changes from Program staff for R-WI, if any | RN | n/a
NOVEMBER
Ask TF to request updated mail lists (GMC, DF, MMAC) | RN | x
Request sector descrip text changes from Program staff | RN
Provide staff photo to RN | TF | x
Staff photo received and placed into AR | RN
Staff photo received and placed into R-WI | RN
Ask MWG: cover letter w/WI Rept (encl. sample)? | RN | x |  | None
AR text and style changes completed | RN
AR text to Program staff for proofing and approval | RN
R-WI text and style changes completed | RN
R-WI text to Program staff for proofing and approval | RN
Grants list to Program staff for editing of descriptions | RN
Sector description text changes to RN | Program
Sector description text changes completed | RN
Sector text to Program staff for proofing and approval | RN
DECEMBER
Provide web-site list of grants to RN | MH
Updated mail lists to RN | TF
Update GMC, DF, MMAC mail lists in E-Tapestry | RN
Run report and export grants from Gifts | R Krebs
Format exported lists for AR | RN
Format exported lists for R-WI | RN
Run Gifts mailing list | RN
Run E-Tapestry mailing list | RN
Combine Gifts and e-Tapestry mail lists | RN
Circulate mail list to Program staff for review | RN
Enter grants into AR document | RN
Enter grants into R-WI document | RN
Run grant tape totals; check all grants entered on AR | R Krebs
Run grant tape totals; check all grants entered on R-WI | R Krebs
Provide AR draft to Program taff | RN
Provide R-WI draft to Program staff | RN
Staff changes on AR returned to RN | Program
Staff changes on R-WI returned to RN | Program
Program Staff changes made to AR | RN
AR changes to Program staff for proofing and approval
Program staff changes made to R-WI | RN
R-WI changes to Program staff for proofing and approval | RN
Provide AR draft to MH | RN
AR draft returned to RN | MH
MH changes to AR completed | RN
AR changes to MH for proofing and approval | RN
Run grant tape total; check all grants entered on AR | R Krebs
Run grant tape total; check all grants entered on R-WI | R Krebs
Prepare reconciliation of grants to financial statement | R Krebs
Provide AR draft to CF w/reconciliation to financial stmt | RN
AR draft returned to RN | CF
Changes to AR completed | RN
AR changes to CF for proofing and approval | RN
Provide AR draft to MWG | RN
AR draft returned to RN | MWG
MWG changes to AR completed | RN
AR changes to MWG for proofing and approval | RN
Provide R-WI draft to MH | RN
R-WI draft returned to RN | MH
MH changes to R-WI completed | RN
R-WI changes to MH for proofing and approval | RN
Provide R-WI draft to CF w/tape totals attached | RN
R-WI draft returned to RN | CF
Changes to R-WI completed | RN
R-WI changes to CF for proofing and approval | RN
Provide R-WI draft to MWG | RN
R-WI draft returned to RN | MWG
MWG changes to R-WI completed | RN
R-WI changes to MWG for proofing and approval | RN
JANUARY
Select foil and ink colors | TF
Return mail list changes to RN | Program
Recommended mail list changes to MWG | RN
Mail list changes returned to RN | MWG
AR mail list changes completed | RN
AR changes to MWG for proofing and approval | MWG/TF
R-WI mail list prepared (pulled from AR mail list) | RN
R-WI mail list to MWG for review | RN
R-WI mail list returned to RN | MWG
R-WI mail list completed | RN
R-WI mail list changes to MWG for proofing and approval | RN
Send AR mail list to printer | RN
Send R-WI mail list to printer | RN
President's letter for R-WI to RN (if needed) | MWG
Draft of President's letter completed | RN
Final of President's letter completed | RN
Letters printed in-house for printer to enclose | RN
Provide final AR draft to MWG/DPS/CF/TF for sign off (ex: FiHi) | RN
Provide final R-WI draft to MWG/DPS/CF/TF for sign off | RN
AR draft returned to RN | VPs
R-WI draft returned to RN | VPs
Changes to AR completed | RN
Changes to editor for proofing and approval | RN
Changes to R-WI completed | RN
Changes to editor for proofing and approval | RN
FEBRUARY
AR mail list sent to printer | RN
R-WI mail list sent to printer | RN
Financial Highlights to RN (as soon after Feb. bd mtg as possible) | MLH
Financial highlights page prepared | RN
Draft of financial highlights to MLH for review | RN
Changes to financial highlights to RN | MLH
Changes to financial highlights completed | RN
Changes to MLH for proofing and approval | RN
Draft of financial highlights to CF for review and sign off | RN
Any changes to financial highlights to RN | CF
Changes to financial highlights completed | RN
Changes to CF for proofing and approval | RN
Draft of financial highlights to MWG for approval | RN
Financial highlights returned to RN | MWG
Financial highlights completed in AR | RN
MARCH
AR packaged by software | RN
R-WI packaged by software | RN
AR CD prepared for printer | RN
R-WI CD prepared for printer | RN
Print color copy of AR for printer | RN
Print color copy of R-WI for printer | RN
CD of AR sent to printer w/color copy print-out | RN
CD of R-WI sent to printer w/color copy print-out | RN
President's letter sent to printer | RN
AR proof received | RN
AR proof reviewed - Program, VPs
AR proof reviewed, signed off | DPS, CF
AR proof reviewed, signed off | MWG
R-WI proof received | RN
R-WI proof reviewed - Program, VPs
R-WI proof reviewed, signed off | DPS, CF
R-WI proof reviewed, signed off | MWG
Changes to AR returned to printer (if any) | RN
Changes to R-WI returned to printer (if any) | RN
New proofs received and reviewed - Program, VPs
Changes to editor for proofing and approval, if any
New proofs received and reviewed - Program, VPs | DPS, CF
AR proof acceptance form signed and returned to printer | DPS, CF
R-WI proof acceptance form signed and returned to printer | Printer
20 AR received | Printer
20 R-WI received
AR mailed by printer
R-WI mailed by printer | Printer
Remainder AR delivered to Fdn. | Printer
Remainder R-WI delivered to Fdn. | RN
Copy to staff - ask MWG 1st about email transmittal | TF/RN
Invoice received | TF/RN
PDF versions emailed to MH for posting on website | RN