## The Bradley Foundation
BNY Mellon Asset Servicing Implementation Plan
Conversion Date:
2011-01-03
Meeting Date: October 29, 2010
The Lynde and Harry Bradley Foundation Task List
| Task Description | Responsibility | Start Date | End Date | Status | Comments
A. | Provide Start Up Information | The Lynde and Harry Bradley Foundation | 2010-11-08 | 2010-11-15
1 | Provide Client Service Officer (CSO) with copy of appointment letter. |  | 2010-11-08 | 2010-11-15
2 | Provide CSO with copy of prior custodian termination letter. If termination letter is delayed, provide interim letter authorizing prior custodian to send asset listings. |  | 2010-11-08 | 2010-11-15
3 | Provide CSO with Conversion Agreement for communication & instructions via e-mail or request password protected files. |  | 2010-11-08 | 2010-11-15
4 | Provide CSO with prior custodian contact information. |  | 2010-11-08 | 2010-11-15
5 | Provide CSO with prior custodian account list. |  | 2010-11-08 | 2010-11-15
6 | Provide CSO with investment manager, fund and private market (if applicable) contacts. |  | 2010-11-08 | 2010-11-15
7 | Provide CSO with all key internal and legal contacts. |  | 2010-11-08 | 2010-11-15
8 | Provide CSO with W-9. If Master Trust, provide by plan. |  | 2010-11-08 | 2010-11-15
9 | Provide CSO with IRS Determination Letter. If Master Trust, provide by plan. |  | 2010-11-08 | 2010-11-15
B. | Provide Legal Agreements | The Lynde and Harry Bradley Foundation | 2010-11-15 | 2010-12-20
1 | Provide Relationship Manager with executed fee schedule. |  | 2010-11-15 | 2010-12-20
2 | Provide CSO with executed Custody and/or Trust Agreement. |  | 2010-11-15 | 2010-12-20
3 | Provide CSO with completed Electronic Access Services Agreement. |  | 2010-11-15 | 2010-12-20
4 | Provide CSO with Supplemental Services Agreement for Transactional Processing if applicable. |  | 2010-11-15 | 2010-12-20
5 | Provide CSO with Performance and Risk Analytics Agreement if applicable. |  | 2010-11-15 | 2010-12-20
6 | Provide CSO with Securities Lending Agreement or third party lending operational guidelines if applicable. |  | 2010-11-15 | 2010-12-20
C. | Provide Account Opening Information | The Lynde and Harry Bradley Foundation | 2010-11-15 | 2010-12-27
1 | Provide CSO with signed account schematic including mapping of prior custodian accounts to new BNYM accounts. |  | 2010-11-15 | 2010-11-22
2 | If internally managed portfolios, determine trading platform, connectivity/transmission requirements, cash reporting and pay requirements. |  | 2010-11-15 | 2010-11-22
3 | Work with CSO to complete account opening information including accounting checklist, proxy voting, corporate actions, and derivatives. |  | 2010-11-22 | 2010-11-29
4 | If other than investment manager, provide vendor or in-house staff requirements for proxy voting. |  | 2010-11-22 | 2010-11-29
5 | Complete investment manager package (applicable for accounts managed by client.) |  | 2010-12-06 | 2010-12-20
6 | Provide CSO list of account consolidations. |  | 2010-12-20 | 2010-12-27
7 | Communicate any changes to account structure prior to conversion date. |  | 2010-12-20 | 2010-12-27
D. | Provide Global Documentation | The Lynde and Harry Bradley Foundation | 2010-11-08 | 2010-12-06
1 | Request that prior custodian provide BNY Mellon with Security Settlement Instructions; assist BNY Mellon with receiving global market data as applicable. |  | 2010-11-08 | 2010-11-15
2 | Provide CSO with authorization letter allowing BNY Mellon to sign global documentation prior to conversion date. |  | 2010-11-15 | 2010-11-22
3 | Provide general power of attorney to allow BNY Mellon to reclaim taxes. |  | 2010-11-15 | 2010-11-22
4 | Provide CSO with IRS 8802 – Application for US residency Certification (required to apply for 6166s- Certification of US Residency). Provide IRS form 8821 – Tax Information Authorization (appoints BNYM to receive client’s tax information). Provide most recent ERISA filing information if applicable. |  | 2010-11-15 | 2010-11-22
5 | Complete global documentation by market for account openings, transfers, tax reclaims and proxy voting as provided by BNY Mellon. Consideration must be given to time frame for account openings by market. |  | 2010-11-15 | 2010-12-06
E. | Discuss Alternative Investments | The Lynde and Harry Bradley Foundation | 2010-11-08 | 2010-12-20
1 | Provide CSO with documentation of any physical real estate holdings. |  | 2010-11-08 | 2010-11-15
2 | Advise if prior trustee signed any LP, real estate, commingled, collective or hedge fund documentation. BNYM to review and document all agreements. Alternative managers may request assignment and assumption letters. |  | 2010-11-15 | 2010-12-20
3 | Confirm accounting procedures for LPs, including cost method and valuations. Advise if any LP's are valued/funded in local currency so BNYM can open local currency accounts accordingly. |  | 2010-12-06 | 2010-12-20
4 | Confirm accounting procedures and valuations for commingled, collective and hedge funds. |  | 2010-12-06 | 2010-12-20
5 | Advise if investment managers are permitted to trade derivatives. |  | 2010-12-13 | 2010-12-20
6 | Provide CSO with options authorization and standing instruction letter for short options if applicable. |  | 2010-12-13 | 2010-12-20
F. | Provide Operational and Audit Documentation | The Lynde and Harry Bradley Foundation | 2010-11-15 | 2010-12-27
1 | Provide CSO with By-Laws, Articles of Incorporation, and/or Legal Status Document (for corporation, not plan.) |  | 2010-11-15 | 2010-11-22
2 | Provide CSO with copies of plan documents for ERISA Qualified DB, Qualified DC, and VEBAS plans. |  | 2010-11-15 | 2010-11-22
3 | Review employer stock requirements with CSO if applicable. |  | 2010-11-15 | 2010-11-22
4 | Provide CSO with Corporate Resolution re: authorized individuals and the authorized signature list. |  | 2010-12-13 | 2010-12-27
5 | Provide CSO with Cash Sweep Letter. If Dreyfus vehicle, also provide Dreyfus Disclosure Letter. |  | 2010-12-13 | 2010-12-27
6 | Provide CSO with FX Procedure Authorization Form as applicable (ERISA clients with global assets.) |  | 2010-12-13 | 2010-12-27
7 | Provide CSO with Operating Standards Agreement (Daily Valued clients) |  | 2010-12-13 | 2010-12-27
G. | Review Requirements of Third Parties and Prior Custodian | The Lynde and Harry Bradley Foundation | 2010-11-08 | 2010-12-27
1 | Identify all third party service providers (consultants, performance measurement, actuaries, etc.). Advise of any custom third party vendor information needs. |  | 2010-11-08 | 2010-11-15
2 | Notify all third parties of change in custodian. Investment Managers should be notified by client prior to distribution of investment managers trading packages. |  | 2010-11-22 | 2010-11-29
3 | Discuss with the prior custodian their plans for handling class action claims prior to conversion date. BNY Mellon will not have the data to file claims for these claims. |  | 2010-12-06 | 2010-12-13
4 | Request a prior custodian/investment manager reconciliation prior to conversion date. |  | 2010-12-20 | 2010-12-27
H. | Review Client Accounting and Reporting Requirements | The Lynde and Harry Bradley Foundation | 2010-11-08 | 2010-12-20
1 | Communicate any additional service requirements including general ledger and custom reporting. If customized service requirements exist, conversion readiness to be reviewed. |  | 2010-11-08 | 2010-11-15
2 | Confirm book of record for conversion if other than current custodian. |  | 2010-11-15 | 2010-11-22
3 | Confirm historic cost value to be used for conversion. |  | 2010-11-15 | 2010-11-22
4 | Communicate reporting needs including deliverable dates, delivery method, core accounting, plan accounting, on-line reports and day one needs. Confirm daily, monthly, quarterly and annual requirements. |  | 2010-12-06 | 2010-12-13
5 | Discuss timing of first month's reporting. Identify accounting requirements accordingly. |  | 2010-12-06 | 2010-12-13
6 | Discuss Cash processes, including standing instructions, repetitive code processing, cash transfers, fee payments and day one needs. |  | 2010-12-06 | 2010-12-13
7 | Discuss procedures regarding investment manager reconciliations. |  | 2010-12-13 | 2010-12-20
I. | Performance Reporting | The Lynde and Harry Bradley Foundation | 2010-11-08 | 2011-02-07
1 | Determine reporting requirements, if applicable. If customized reporting needs exist, conversion readiness to be reviewed. |  | 2010-11-08 | 2010-11-15
2 | Receive P&RA mailboxes for e-mail communications, if applicable. |  | 2010-11-29 | 2010-12-06
3 | Identify performance reporting requirements as outlined in due diligence questionnaire and other relevant documents/information |  | 2010-12-06 | 2010-12-13
4 | Discuss timing of first month's reporting. Identify performance measurement requirements accordingly. |  | 2010-12-06 | 2010-12-13
5 | Provide daily/monthly benchmarks, and custom or blended if required. |  | 2010-12-13 | 2010-12-20
6 | Determine performance account structure/consolidation accounts. |  | 2010-12-20 | 2010-12-27
7 | Determine historical gross and net requirements (including availability, source, individual and consolidation account inception date.) |  | 2010-12-20 | 2010-12-27
8 | Provide sign off on historical performance measurement data for individual and consolidated accounts. |  | 2011-01-31 | 2011-02-07
J. | Analytics, Attribution, Universe, Compliance Monitoring | The Lynde and Harry Bradley Foundation | 2010-12-20 | 2010-12-27
1 | Review Analytics service offerings with P&RA. |  | 2010-12-20 | 2010-12-27
2 | Review Attribution service offerings with P&RA. |  | 2010-12-20 | 2010-12-27
3 | Identify the appropriate benchmarks for Attribution reporting |  | 2010-12-20 | 2010-12-27
4 | Review Universe service offerings with P&RA. |  | 2010-12-20 | 2010-12-27
5 | Review Compliance Monitoring offerings with P&RA. |  | 2010-12-20 | 2010-12-27
6 | Receive training on Analytics/Attribution/Universes/Compliance, as applicable |  | 2010-12-20 | 2010-12-27
K. | Workbench Set-up and Training | The Lynde and Harry Bradley Foundation | 2010-12-06 | 2011-02-28
1 | Provide CSO with Workbench user information to facilitate ID set up (user names, phone numbers, email addresses, and levels of access.) |  | 2010-12-06 | 2010-12-13
2 | Work with CSO & Workbench Consultant to determine training requirements and schedule product demonstrations. |  | 2010-12-06 | 2011-01-03
3 | Work with CSO & Workbench Consultant to schedule additional training and product sessions as applicable. |  | 2011-01-03 | 2011-02-28
L. | Treasury Services | The Lynde and Harry Bradley Foundation | 2010-11-08 | 2010-11-19
1 | Provide Treasury Services, Project Leader, with required forms |  | 2010-11-08 | 2010-11-19
M. | Deliverables | The Lynde and Harry Bradley Foundation | 2011-02-14 | 2011-03-21
1 | Receive 1st set of accounting deliverables. |  | 2011-02-14 | 2011-02-28
2 | Receive 1st set of performance deliverables. |  | 2011-02-28 | 2011-03-14
3 | Provide CSO with conversion reconcilement approval. |  | 2011-02-28 | 2011-03-21
4 | Discuss open items. |  | 2011-03-14 | 2011-03-21
5 | Project close / hand off to servicing team. |  | 2011-03-14 | 2011-03-21
Formulas:
Start Date = MIN([Start Date, row below]:D22)
End Date = MAX([End Date, row below]:E22)