## GO Conversion External
Priority |  | Issue | Comment/Question | Explanation | Status | Resolution
done | External | Question | Alerts for requirements | can coming up requirement due dates be captured in an automatic error report? | Yes, a report can be created and scheduled. An email can be sent to users to remind of requirements and activities. | yes
done | External | Question | Can a list of saved searches from GIFTS be obtained for review? | To compare Gifts to GO | email to NK - received | yes
done | External | Question | Can payments be scheduled before a grant is approved? Can payments be paid in batch? | yes per NK | use the approval wizard? | yes
done | External | Question | Can users be prompted to complete a requirement? | email reminder? | on a dashboard part | yes
done | External | Question | Can we update in batch? | Gifts Plus included with GO? |  | yes
done | External | Question | Checking documents in and out | how does this work? Sharepoint | doc. Is checked out and in when updates are made. Functionality only available using IE | yes
done | External | Question | GO category radio button display | can default be set to have all radio buttons display | customized display per user | yes
done | External | Question | GO number of record display | can all page views be changed to default to 100 records vs 5? | customized display per user | yes
done | External | Question | GO search functionally 'wild' characters | what are wild characters? Has search functionality become better with GO vs Gifts? | * | yes
done | External | Question | grant requirements | does the system still allow payment even though a requirement has not been marked done? does marking a payment contingent put a hold on releasing the payment? | yes if it isn't a required requirement. | yes
done | External | Question | How are record counts obtained from GO database? | need to compare db record count sent vs received in GO | received from NK | yes
done | External | Question | Review 'Fields in Use' and field purpose | can fields not in use be omitted? | yes if we have Blueprint | yes
done | External | Question | Who is Program Officer Administrator, Program Officer dashboard for? |  | removed by NK | yes
done | External | Training Demo | coding multiple addresses for one professor | Bradley Fellows-some administrative assistance to professors would like multiple addresses for letters. Stanford example. | only one address can be used as primary address | yes
done | External | When | Set up benchmarking meeting with CF and TF to define tasks | cc: MicroEdge, Nehama, Scott Larson, Adam Fox, Nick Gustafson, Adam Becker? on open tasks to be completed. Ask Nehama for documented time allocation to project | bi-weekly meetings set up | yes
done | External | When | Training Admin Tasks | Who? When? | RK, DK, CF | yes
done | External | When | Training Basics, overview, processing requests, navigation, letters, updates, emails | Who? When? | All | yes
done | External | When | Training Budget Module | Who? When? | RK, LD, MJH, MH, CF | yes
done | External | When | Training Search/Reports/ Views | Who? When? | All | yes
done | External | When | Training A/P Module, Great Plains integration | Who? When? | per NK taining not required | yes
done | External |  | Full Search on 2014 BF off $25,000 in GO | why? Email to Nehama 3-11-15. GO is missing id#20140945 Stanford | search ran ok on 3-12-15 | yes
* | External | Question | 50 custom fields in Gifts online | Fields can be created at our convenience.. Name of field, Type of data stored (text, numeric, currency, date, etc.) and record type (org, req, contact, requirement, etc). 50 available. Use for BF? code Gifts to track 4942(g)(3) grants must track the grantees to make sure they return the payment from corpus election | email to Nehama 3/11/15 | pending
* | External | Question | Budget Module On or Off | will 1 quarter data transfer (allocations)
* | External | Question | Can a list of saved views from GIFTS be obtained for review? | To compare Gifts to GO | email to NK | pending
* | External | Question | Follow up with MicroEdge help desk regarding the 'as of' date and timing for resolution | for payment due schedule by program area one report and Sch of Appro.
* | External | Question | GO Work Plan moving forward |  |  | pending
* | External | Question | Migration - if we migrate and functionality doesn't work will the fixes be in place by the end of the blackout?
* | External | Question | NEW IRS Tax codes - added to Gifts - need codes from NK | can a 'global' add be done? What is MicroEdge update on new tax code implementation with Gifts?
* | External | Question | Processing Payments
* | External | Question | Report fix date | payment due schedule, error when running Dec search
* | External | Question | Tax Code Look up | does not work - need codes from NK entered
* | External | Question | Templates, Reports, Views, Searches | should all be transferred to GO?
* | External | Question | Test Database available during blackout period?
| External | Question | Can fields in templates be locked? | ex: project title populated in GPR form. This would eliminate inconsistencies Gifts vs Word document
| External | Question | Can Grant history process be modified?
| External | Question | Can inactive codes be omitted from displaying in pull down menus?
| External | Question | Can recommended auto fill default to zero?
| External | Question | coding addresses in Gifts | Shug gets proposals, alisha Birth gets checks, how should this be set up? Grant ID 20131248
| External | Question | coding at organization level vs request level | find out what governs field population. If coded at organization level do those codes populate the request field? If there are not codes entered at the organization level how do codes get populated at the request level?
| External | Question | Declining a proposal | should affiliations be closed when declining a proposal?
| External | Question | Do we have IGAM with GO?
| External | Question | F3 key to populate date | does this work in GO?
| External | Question | Follow up with MocroEdge regarding next release date for GO | as of 3-10-15 no release date scheduled
| External | Question | Gifts document storage on 'J' drive | where will these documents be stored? On 'J' drive or cloud? Jan renames her documents for retrieval later | J' drive will not be available with GO. How are doc's. updated? Do they need to be checked in and out? How to save a doc. To the cloud
| External | Question | How long will we have old Gifts database available after conversion
| External | Question | IRS look up | codes need to be set up in GO |  | pending
| External | Question | Request Status field 'Active Grant' vs 'Closed Grant' | does this happen automatically or does each grant need to be manually closed? Batch?
| External | Question | Signer Auto Fill | what is default?
| External | Training Demo | Change Status
| External | Training Demo | Checklists
| External | Training Demo | Contingency Grants/Challenge | ex MPM 20130477 over 5 years. What restricts system from releasing payment?
| External | Training Demo | Create File Folder labels in Batch
| External | Training Demo | Declination Letters
| External | Training Demo | Gpr's
| External | Training Demo | How are contingencies handled in Gifts ref: Encounter 20140494 approved at 8/19/14 board meeting to be paid in 2014
| External | Training Demo | How should RFP grants be handled? | One large grant entered into Gifts to be allocated to individual grants
| External | Training Demo | Letter editing | work around for editing 'To' to 'to', removing table headers, adding carbon copies, etc.
| External | Training Demo | Processing Payments
| External | Training Demo | Run Pending Log
| External | Training Demo | Update Contacts and Addresses
| External | Training Demo | uploading Documents | ex: progress report, 990, etc.
| External | When | Coding Sheet configuration
| External | When | Create report forms
| External | When | Deactivate old codes | what is timing for this?
| External | When | Define New Code Tables | in test database
| External | When | Mobile app client login ID | Who? When? | All
| External | When | New report set up | post migration
| External | When | Omit old letter templates
| External | When | Optimize process and data structure
| External | When | Purge removed documents | get guidance from MicroEdge before migration
| External | When | Report - Duplicate Contact report from Gifts
| External | When | Report - Duplicate Organization report from Gifts | to review for errors
| External | When | Report - paid grants not marked as closed | get guidance from MicroEdge before migration
| External | When | Report - to confirm that all payments are marked Paid | get guidance from MicroEdge before migration
| External | When | Run Recalculate Utility | get guidance from MicroEdge before migration
| External | When | Set up Budget Module
| External | When | System Code Configuration
| External | When | Templates | determine which templates to convert
| External | When | Training | initial corres. With Colleen designated on site training requires a minimum of 2 days consulting $3520 travel exp $500 travel. Webinar sharing session training $220/hr estimated 8 hours - 3 days of training 1. basics, 2. Search/reports, 3. Admin tasks
| External | When | Transfer Gifts database to MicroEdge for 2nd migration | afternoon on 3/31/15

## GO Conversion Internal
Priority |  | Issue | Comment/Question | Explanation | Status | Resolution
done | Internal | Question | How to handle invoices | Invoices will be initialed by Rk and then given to TF | optional to create sub categories | 2015-03-12
done | Internal | Question | How to handle invoices | Invoices will be initialed by Rk and then given to TF | optional to create sub categories | 2015-03-12
done | Internal | Training Demo | Set up MicroEdge training in RCR | emailed Dan and Dionne regarding training date preference
done | Internal | Training Demo | Set up MicroEdge training in RCR | emailed Dan and Dionne regarding training date preference
| Internal | Data Verify | Test Activity
| Internal | Data Verify | Test Affiliation
| Internal | Data Verify | Test Cancelation
| Internal | Data Verify | Test Checks
| Internal | Data Verify | Test Compliance Checklist
| Internal | Data Verify | Test Contracts
| Internal | Data Verify | Test Envelopes
| Internal | Data Verify | Test GPR | write how to instructions
| Internal | Data Verify | Test Grant History
| Internal | Data Verify | Test letters | award, dec, OM, Prelim, BF, etc
| Internal | Data Verify | Test Monthly reports
| Internal | Data Verify | Test New Contact
| Internal | Data Verify | Test New Request
| Internal | Data Verify | Test Refund
| Internal | Data Verify | Test Reissue
| Internal | Data Verify | Test Reporting | match to 12/31/14 reports and 2015
| Internal | Data Verify | Test Requirements
| Internal | Data Verify | Test Search and Views
| Internal | Data Verify | Test User 'Gifts' functions others perform
| Internal | Data Verify | Test Void
| Internal | Data Verify | Test Wire
| Internal | License Issue | release test database to staff | only 11 lic. Released to RK, DK, DL, AM, DS, DJS, JR, MH, LD - SM and MWG pending. add lic. for TF, CF, MJH, RN, KP, SM, WB, finance? Can A grants mgr lic. be switched to a program officer lic? Do we want the grant manager functionality given to DL and DK? See permissions. Re: payments/security and deleting permission rights. Are our licenses tied to users or is it concurrent lic? Can a new email address be created to multiple users to share? | LD needs more than view only access (procedure change for import/export?) email to TF 3-12-14. Nick G to send invoice to the Foundation | pending
| Internal | Procedure | Document procedures/Training Documentation for GO |  |  | pending
| Internal | Procedure | Map Process Flow - Flow Charts - Gifts Online | 1st migration |  | pending
| Internal | Procedure | Memo to program staff regarding primary contact info. In Gifts - 'address block' uses the contact information from the request and Proposal entry consistency | cc: CF, DL, DK. CF asked TF for a list of tasks that DL does. Standardization for field entry Pending. | list from TF re: DL tasks preformed in Gifts | pending
| Internal | Procedure | signed grant agreements do not designate where to return | signed agreements float around the bldg. rather than being sent to one area. Ie. If addresses to the Bradley Fdn. Terri received, Dan receives, Mike, and Program staff. | procedure change? | pending
| Internal | Procedure | Training Documentation |  |  | pending